## Read Me
Parametric Digital Platform — Azure to AWS Migration
Discovery Workshops — per-application capture, and wave-plan engine · Workstream B (Vertical Relevance)
What this workbook is
A production-ready discovery + capture instrument for the pre-engagement workshops. VR's workshop structure is the baseline; a broader production-readiness domain bank is merged in to fill gaps. As each SME speaks, we capture the answer AND the risks, dependencies, and assumptions in the same place — those facts then drive the application disposition and the migration wave plan.
How to use it (the flow)
1. RACI first — confirm who owns what and who approves.
2. Run the workshops (tabs named per VR's schedule). Filter the Questions tab by Workshop to build each session's pack.
3. Capture live on the per-application tabs (SMAP / IPORT / IMAT / .com): Answer, plus Risk / Dependency / Assumption / Decision-needed / Owner.
4. Captured facts feed the DISPOSITION automatically — e.g. 'runs on Azure SQL' -> 'target Amazon RDS SQL Server' (two birds, one stone).
5. Dependencies feed the Dependency Register and the Engine -> Move Groups -> Waves -> Program Roadmap.
The design in one line (for the internal walkthrough)
Discovery questions -> captured facts (+risk/dep/assumption) -> per-app disposition -> move groups -> waves -> roadmap.
See tab 'Walkthrough / Design' for the end-to-end narrative with the SMAP/IPORT/IMAT worked example.
Tabs
Read Me · SME Time Commitment (Parametric commitment) · Questions (Core Discovery + Prod-Ready) · Walkthrough / Design · App tabs: SMAP · IPORT · IMAT · .com · Platform: LZ/Radius · Service Onboarding · App Dispositioning · Data-DB Deep Dive · RACI · Program Roadmap · Integrations (on-prem & 3rd-party) · Azure → AWS Mapping · Dependency Register · RAID Log · Wave Plan.
Source legend (traceability — defend every question)
Every question carries a Source tag, on the Questions tab AND on each app tab:
• 'Core' = VR team architecture discovery questions per application.
• 'Other Prod-ready' = Other production-readiness questions ensuring complete Azure->AWS coverage (traffic/TPS, rate limiting, p95/p99 latency, hard-coded IPs, scalability, HA/DR, observability) — the specifics SMEs won't volunteer unless explicitly asked.
Filter the Source column on any tab to separate the two instantly.

## SME Time Commitment
Parametric SME Time Commitment — hours we're requesting from your team
These are the SME hours per workshop we need Parametric to allocate across the 12-week pre-engagement so VR can run discovery and build the production-ready migration plan. Estimates are conservative.
How it's scheduled is Parametric's call: each workshop's hours can run as ONE session or be split across MULTIPLE shorter sessions. VR delivery time is covered under the pre-engagement and is not part of this ask.
Workshop | SME time | Sessions (client's choice) | Target week | SME roles to involve
RACI Overview | 1 hr | 1 or more — client decides |  | Decision owners / leads across app, platform, security, data
High-Level Application Portfolio Review | 4-6 hrs | 1 or more — client decides |  | App owners for SMAP, IPORT, IMAT, .com (+ architects)
AWS LZ & Shared Infrastructure Foundation | 3-4 hrs | 1 or more — client decides |  | Platform / Landing-Zone / networking / IAM owners
Service Onboarding Framework | 1-2 hrs | 1 or more — client decides |  | Service-onboarding + SecArch representatives
Application Dispositioning Framework | 1-2 hrs | 1 or more — client decides |  | Architecture + SecArch + disposition approvers
Data / DB Inventory Deep Dive | 1-2 hrs | 1 or more — client decides |  | DBAs + data-platform owners
Program Roadmap / Wave Plan | 1-2 hrs | 1 or more — client decides |  | Leads + decision owners (Parametric / MS / AWS)
TOTAL SME time commitment | ~12–19 hrs | across the pre-engagement |  | seven workshops ?
Note: the Portfolio Review covers 4 applications (SMAP / IPORT / IMAT / .com) — Parametric may run it as a single long session or one session per app; either way the total SME time is ~4–6 hrs. 'Target week' is left blank for Parametric to assign.

## Questions
Questions — Core Discovery + Prod-Ready questions, categorized by workshop. Filter by Source, Workshop or Application.
ID | Workshop | Topic / Domain | Application | SME Role | Question | Why we ask / feeds | Source | Pre-fill async?
RACI Overview
Q001 | RACI Overview | Approvals | N/A |  | Who approves SecArch, architecture, production readiness, CAB/change and business go/no-go? |  | Core
Q002 | RACI Overview | Decision ownership | N/A |  | Who is accountable for application disposition, target architecture and migration sequencing decisions? |  | Core
Q003 | RACI Overview | Delivery ownership | N/A |  | During migration/cutover/hypercare, what is owned by Parametric/MS, AWS and VR, and where does ownership transition? |  | Core
Q004 | RACI Overview | Domain ownership | N/A |  | Who owns application, network, security/IAM, data/DB, platform/LZ, observability and CI/CD decisions/inputs? |  | Core
Q005 | RACI Overview | Escalation | N/A |  | What is the escalation path when a dependency, shared service or approval threatens the roadmap? |  | Core
High-Level Application Portfolio Review
Q006 | High-Level Application Portfolio Review | Application Profile | (any app / general) | App Owner | What is the application's business purpose and who are its primary users (internal, partner, public)? | Business criticality; Red Zone exposure | Other Prod-ready | Yes
Q007 | High-Level Application Portfolio Review | Application Profile | (any app / general) | App Owner | What is the business criticality tier (e.g. Tier 1 critical / Tier 2 important / Tier 3 standard) and why? | Criticality modifier for wave sequencing | Other Prod-ready | Yes
Q008 | High-Level Application Portfolio Review | Application Profile | (any app / general) | App Owner | Is this application public-facing / internet-exposed, partner-facing, or internal-only? | Red Zone (Akamai→API GW→ALB) requirement | Other Prod-ready | Yes
Q009 | High-Level Application Portfolio Review | Application Profile | (any app / general) | App Owner | What business processes break if this app is down for 1 hour? 4 hours? 1 day? | Downtime tolerance; RTO | Other Prod-ready | Yes
Q010 | High-Level Application Portfolio Review | Application Profile | (any app / general) | App Owner | Are there seasonal / cyclical peaks (month-end, quarter-end, trading hours) that constrain cutover windows? | Cutover window scheduling | Other Prod-ready | Yes
Q011 | High-Level Application Portfolio Review | Application Profile | (any app / general) | App Owner | Is the application subject to regulatory / compliance obligations (SOX, SEC, PCI, data residency)? | Security gate; cutover controls | Other Prod-ready | Yes
Q012 | High-Level Application Portfolio Review | Application Profile | (any app / general) | App Owner | Who is the technical owner and who signs off go/no-go for this app's cutover? | RACI; cutover approval | Other Prod-ready | Yes
Q013 | High-Level Application Portfolio Review | Application Profile | (any app / general) | App Owner | Is the app actively developed, in maintenance, or candidate for retire/replace? | 7R: Retire vs Rehost vs Replatform | Other Prod-ready | Yes
Q014 | High-Level Application Portfolio Review | Application Profile | (any app / general) | App Owner | Are there any planned business changes (M&A, product sunset) that affect migration timing? | Wave timing risk | Other Prod-ready | Yes
Q015 | High-Level Application Portfolio Review | Application Profile | (any app / general) | Business | What is the acceptable business downtime for cutover and is a maintenance window pre-approved? | Downtime tolerance; RTO | Other Prod-ready | Yes
Q016 | High-Level Application Portfolio Review | Application dependencies | SMAP |  | What are the key upstream/downstream, on-prem, AWS/Radius, shared-service and external dependencies? What systems are communicated with outside of Azure? |  | Core
Q017 | High-Level Application Portfolio Review | Application dependencies | IPORT |  | What are the key upstream/downstream, on-prem, AWS/Radius, shared-service and external dependencies? What systems are communicated with outside of Azure? |  | Core
Q018 | High-Level Application Portfolio Review | Application dependencies | IMAT |  | What are the key upstream/downstream, on-prem, AWS/Radius, shared-service and external dependencies? What systems are communicated with outside of Azure? |  | Core
Q019 | High-Level Application Portfolio Review | Application dependencies | .com |  | What are the key upstream/downstream, on-prem, AWS/Radius, shared-service and external dependencies? What systems are communicated with outside of Azure? |  | Core
Q020 | High-Level Application Portfolio Review | Architecture | (any app / general) | App Owner | What is the application architecture (monolith, microservices, N-tier, serverless)? | Target compute (ECS Fargate) sizing | Other Prod-ready | Yes
Q021 | High-Level Application Portfolio Review | Architecture | (any app / general) | App Owner | Which Azure App Service plan(s) host it, and Windows or Linux? | Containerization effort; ECS fit | Other Prod-ready | Yes
Q022 | High-Level Application Portfolio Review | Architecture | (any app / general) | App Owner | What language/runtime and framework versions (e.g. .NET Framework vs .NET Core, Node, Java)? | .NET Framework => containerization risk | Other Prod-ready | Yes
Q023 | High-Level Application Portfolio Review | Architecture | (any app / general) | App Owner | Is the app already containerized (Docker)? If not, any blockers to containerizing (Win auth, GAC, COM, native deps)? | ECS Fargate readiness | Other Prod-ready | Yes
Q024 | High-Level Application Portfolio Review | Architecture | (any app / general) | App Owner | How many environments exist (dev/test/stage/prod) and do they differ materially? | Scope; pattern reuse | Other Prod-ready | Yes
Q025 | High-Level Application Portfolio Review | Architecture | (any app / general) | App Owner | What are current compute sizing / scaling settings (instance count, autoscale rules, CPU/mem)? | Right-sizing on ECS | Other Prod-ready | Yes
Q026 | High-Level Application Portfolio Review | Architecture | (any app / general) | App Owner | Does the app rely on in-memory session / sticky sessions / local disk state? | Statelessness; ALB config; EFS need | Other Prod-ready | Yes
Q027 | High-Level Application Portfolio Review | Architecture | (any app / general) | App Owner | Are there Windows-specific dependencies (IIS modules, Windows auth/Kerberos, MSMQ, scheduled tasks)? | Replatform complexity | Other Prod-ready | Yes
Q028 | High-Level Application Portfolio Review | Architecture | (any app / general) | App Owner | Any WebJobs / background workers / cron inside the App Service? | ECS task vs EventBridge Scheduler | Other Prod-ready | Yes
Q029 | High-Level Application Portfolio Review | Architecture | (any app / general) | App Owner | What is the config/secret injection method today (App Settings, Key Vault refs, env vars)? | Secrets Manager migration | Other Prod-ready | Yes
Q030 | High-Level Application Portfolio Review | Architecture walkthrough | SMAP |  | Can you walk us through the high-level architecture diagram for SMAP? |  | Core
Q031 | High-Level Application Portfolio Review | Architecture walkthrough | IPORT |  | Can you walk us through the high-level architecture diagram for IPORT? |  | Core
Q032 | High-Level Application Portfolio Review | Architecture walkthrough | IMAT |  | Can you walk us through the high-level architecture diagram for IMAT? |  | Core
Q033 | High-Level Application Portfolio Review | Architecture walkthrough | .com |  | Can you walk us through the high-level architecture diagram for .com? |  | Core
Q034 | High-Level Application Portfolio Review | Architecture walkthrough | SMAP |  | How does SMAP interface with shared service domains such as networking, security and access, database, compute, etc.? |  | Core
Q035 | High-Level Application Portfolio Review | Architecture walkthrough | IPORT |  | How does IPORT interface with domains such as networking, security and access, database, compute, etc.? |  | Core
Q036 | High-Level Application Portfolio Review | Architecture walkthrough | IMAT |  | How does IMAT interface with domains such as networking, security and access, database, compute, etc.? |  | Core
Q037 | High-Level Application Portfolio Review | Architecture walkthrough | .com |  | How does .com interface with domains such as networking, security and access, database, compute, etc.? |  | Core
Q038 | High-Level Application Portfolio Review | Business context | SMAP |  | What is the general business purpose of SMAP? |  | Core
Q039 | High-Level Application Portfolio Review | Business context | IPORT |  | What is the general business purpose of IPORT? |  | Core
Q040 | High-Level Application Portfolio Review | Business context | IMAT |  | What is the general business purpose of IMAT? |  | Core
Q041 | High-Level Application Portfolio Review | Business context | .com |  | What is the general business purpose of .com? |  | Core
Q042 | High-Level Application Portfolio Review | Business context | SMAP |  | Who are the user personas for SMAP? How do they access the portal? |  | Core
Q043 | High-Level Application Portfolio Review | Business context | IPORT |  | Who are the user personas for IPORT? How do they access the portal? |  | Core
Q044 | High-Level Application Portfolio Review | Business context | IMAT |  | Who are the user personas for IMAT? How do they access the portal? |  | Core
Q045 | High-Level Application Portfolio Review | Business context | .com |  | Who are the user personas for .com? How do they access the portal? |  | Core
Q046 | High-Level Application Portfolio Review | Business context | SMAP |  | How often is SMAP used? |  | Core
Q047 | High-Level Application Portfolio Review | Business context | IPORT |  | How often is IPORT used? |  | Core
Q048 | High-Level Application Portfolio Review | Business context | IMAT |  | How often is IMAT used? |  | Core
Q049 | High-Level Application Portfolio Review | Business context | .com |  | How often is .com used? |  | Core
Q050 | High-Level Application Portfolio Review | Domain-specific questions | SMAP |  | What are the SLA requirements for this portal? What are the RPO and RTO? |  | Core
Q051 | High-Level Application Portfolio Review | Domain-specific questions | IPORT |  | What are the SLA requirements for this portal? What are the RPO and RTO? |  | Core
Q052 | High-Level Application Portfolio Review | Domain-specific questions | IMAT |  | What are the SLA requirements for this portal? What are the RPO and RTO? |  | Core
Q053 | High-Level Application Portfolio Review | Domain-specific questions | .com |  | What are the SLA requirements for this portal? What are the RPO and RTO? |  | Core
Q054 | High-Level Application Portfolio Review | Domain-specific questions | SMAP |  | What are the high-availability capabilities of the application? |  | Core
Q055 | High-Level Application Portfolio Review | Domain-specific questions | IPORT |  | What are the high-availability capabilities of the application? |  | Core
Q056 | High-Level Application Portfolio Review | Domain-specific questions | IMAT |  | What are the high-availability capabilities of the application? |  | Core
Q057 | High-Level Application Portfolio Review | Domain-specific questions | .com |  | What are the high-availability capabilities of the application? |  | Core
Q058 | High-Level Application Portfolio Review | Domain-specific questions | SMAP |  | What are the DR capabilities of the application? (backup&restore, pilot light, warm standby, active/active) |  | Core
Q059 | High-Level Application Portfolio Review | Domain-specific questions | IPORT |  | What are the DR capabilities of the application? (backup&restore, pilot light, warm standby, active/active) |  | Core
Q060 | High-Level Application Portfolio Review | Domain-specific questions | IMAT |  | What are the DR capabilities of the application? (backup&restore, pilot light, warm standby, active/active) |  | Core
Q061 | High-Level Application Portfolio Review | Domain-specific questions | .com |  | What are the DR capabilities of the application? (backup&restore, pilot light, warm standby, active/active) |  | Core
Q062 | High-Level Application Portfolio Review | Domain-specific questions | SMAP |  | What do you perceive to be the most challenging or complex part(s) of the portal? |  | Core
Q063 | High-Level Application Portfolio Review | Domain-specific questions | IPORT |  | What do you perceive to be the most challenging or complex part(s) of the portal? |  | Core
Q064 | High-Level Application Portfolio Review | Domain-specific questions | IMAT |  | What do you perceive to be the most challenging or complex part(s) of the portal? |  | Core
Q065 | High-Level Application Portfolio Review | Domain-specific questions | .com |  | What do you perceive to be the most challenging or complex part(s) of the portal? |  | Core
Q066 | High-Level Application Portfolio Review | HA & DR | (any app / general) | Ops/SRE | What are the current HA settings (zones, instances, load balancing)? | Multi-AZ target design | Other Prod-ready | Yes
Q067 | High-Level Application Portfolio Review | HA & DR | (any app / general) | Ops/SRE | What are the formal RTO and RPO targets for this application? | DR design; cutover method | Other Prod-ready | Yes
Q068 | High-Level Application Portfolio Review | HA & DR | (any app / general) | Ops/SRE | Is there a documented DR plan and when was it last tested? | DR gate | Other Prod-ready | Yes
Q069 | High-Level Application Portfolio Review | HA & DR | (any app / general) | Ops/SRE | Is multi-region required (us-west-2 / us-east-1) or single-region acceptable? | Region strategy; cost | Other Prod-ready | Yes
Q070 | High-Level Application Portfolio Review | HA & DR | (any app / general) | Ops/SRE | What backup/restore tooling is used and what are retention requirements? | Backup design; DC-exit | Other Prod-ready | Yes
Q071 | High-Level Application Portfolio Review | Integration | (any app / general) | Integration | List every system this app CALLS (synchronous APIs, DB, queue, file) — internal and external. | Dependency graph edges | Other Prod-ready | Yes
Q072 | High-Level Application Portfolio Review | Integration | (any app / general) | Integration | List every system that CALLS this app (upstream consumers). | Dependency graph edges | Other Prod-ready | Yes
Q073 | High-Level Application Portfolio Review | Integration | (any app / general) | Integration | Does the app use Azure Service Bus (queues/topics)? Which namespaces and for what flows? | SQS/SNS/EventBridge mapping | Other Prod-ready | Yes
Q074 | High-Level Application Portfolio Review | Integration | (any app / general) | Integration | Does the app publish/consume Event Hubs streams? | Kinesis mapping | Other Prod-ready | Yes
Q075 | High-Level Application Portfolio Review | Integration | (any app / general) | Integration | Does it depend on APIM-fronted APIs? Which, and are they internal or partner? | API Gateway; Red Zone | Other Prod-ready | Yes
Q076 | High-Level Application Portfolio Review | Integration | (any app / general) | Integration | Are there partner / third-party integrations (Salesforce, SendGrid, payment, market data)? Auth method? | External connectivity; DC-exit | Other Prod-ready | Yes
Q077 | High-Level Application Portfolio Review | Integration | (any app / general) | Integration | Does the app reach on-prem systems (PCR, Argos, Union, AD, file shares, SFTP)? Over what connectivity? | Hybrid connectivity; move-before vs stay | Other Prod-ready | Yes
Q078 | High-Level Application Portfolio Review | Integration | (any app / general) | Integration | For each on-prem dependency: must it move BEFORE, WITH, LATER, can it STAY, or is it a DC-exit blocker? | The 5-question disposition — drives wave | Other Prod-ready | No
Q079 | High-Level Application Portfolio Review | Integration | (any app / general) | Integration | Are there hard-coded IPs, hostnames, or on-prem DNS names in config or code? | DNS cutover risk; refactor | Other Prod-ready | Yes
Q080 | High-Level Application Portfolio Review | Integration | (any app / general) | Integration | What authentication is used between services (mTLS, API keys, OAuth, Windows auth)? | IAM/secrets; refactor effort | Other Prod-ready | Yes
Q081 | High-Level Application Portfolio Review | Integration | (any app / general) | Integration | Are there scheduled file transfers (SFTP) in/out? Endpoints and schedules? | Transfer Family; DC-exit | Other Prod-ready | Yes
Q082 | High-Level Application Portfolio Review | Integration | (any app / general) | Integration | Does the app send email (SMTP / SendGrid)? Relay host? | SES/SendGrid; connectivity | Other Prod-ready | Yes
Q083 | High-Level Application Portfolio Review | Other Workshop | N/A |  | Do you know answers/context on the LZ & Shared Infrastructure Foundations questions? Any people you recommend we include? |  | Core
Q084 | High-Level Application Portfolio Review | Other Workshop | N/A |  | Do you know answers/context on the Service Onboarding questions? Any people you recommend we include? |  | Core
Q085 | High-Level Application Portfolio Review | Other Workshop | N/A |  | Do you know answers/context on the Application Dispositioning questions? Any people you recommend we include? |  | Core
Q086 | High-Level Application Portfolio Review | Performance & SLA | (any app / general) | Ops/SRE | What are the current latency numbers (p50/p95/p99) for key transactions? | Target perf baseline; validation gate | Other Prod-ready | Yes
Q087 | High-Level Application Portfolio Review | Performance & SLA | (any app / general) | App Owner | What latency/response-time SLA or user expectation must be preserved post-migration? | Design target; go/no-go criterion | Other Prod-ready | Yes
Q088 | High-Level Application Portfolio Review | Performance & SLA | (any app / general) | App Owner | What availability SLA/SLO applies (e.g. 99.9%)? Is it contractual? | Multi-AZ/region; design target | Other Prod-ready | Yes
Q089 | High-Level Application Portfolio Review | Performance & SLA | (any app / general) | Ops/SRE | What is the current CPU/memory utilization profile (avg & peak) per component? | Right-sizing; task/instance selection | Other Prod-ready | Yes
Q090 | High-Level Application Portfolio Review | Performance & SLA | (any app / general) | DBA | What are database latency hotspots (slow queries, lock contention, long transactions)? | RDS/Aurora instance class; read replicas | Other Prod-ready | Yes
Q091 | High-Level Application Portfolio Review | Performance & SLA | (any app / general) | Ops/SRE | Are there components sensitive to cold starts or warm-up (JIT, cache priming, connection pools)? | Provisioned concurrency; warm pools | Other Prod-ready | Yes
Q092 | High-Level Application Portfolio Review | Performance & SLA | (any app / general) | Ops/SRE | Is there a documented performance/load test baseline we can replay on AWS to compare? | Perf validation; sign-off | Other Prod-ready | Yes
Q093 | High-Level Application Portfolio Review | Performance & SLA | (any app / general) | App Owner | Which transactions are latency-critical vs tolerant (user-facing vs background)? | Tiered design; placement | Other Prod-ready | Yes
Q094 | High-Level Application Portfolio Review | Performance & SLA | (any app / general) | Network | What is the latency budget between tiers (web→app→DB→dependency) and any sub-ms sensitivity? | Co-location; AZ placement; cluster placement | Other Prod-ready | Yes
Q095 | High-Level Application Portfolio Review | Refactor candidacy | IMAT |  | What specific design components / attributes of IMAT make it a candidate to be refactored? |  | Core
Q096 | High-Level Application Portfolio Review | SME/Ownership | All |  | Which Parametric/MS teams or SMEs own the key application dependencies and integrations? |  | Core
Q097 | High-Level Application Portfolio Review | Scalability | (any app / general) | App Owner | What is the 1–3 year growth projection (users, transactions, data) for this app? | Capacity design; reserved vs on-demand | Other Prod-ready | Yes
Q098 | High-Level Application Portfolio Review | Scalability | (any app / general) | Ops/SRE | What is the current scaling model (vertical, horizontal, manual, auto) and its triggers? | Target autoscaling policies | Other Prod-ready | Yes
Q099 | High-Level Application Portfolio Review | Scalability | (any app / general) | App Owner | Is the workload elastic (scales to zero / scales down off-hours) or always-on? | Fargate/Lambda/scheduled scaling; cost | Other Prod-ready | Yes
Q100 | High-Level Application Portfolio Review | Scalability | (any app / general) | Ops/SRE | Are there hard ceilings today (license cores, connection pools, single-threaded components)? | Scaling bottlenecks; redesign flag | Other Prod-ready | Yes
Q101 | High-Level Application Portfolio Review | Scalability | (any app / general) | DBA | What are the database scaling limits (max connections, IOPS, storage) hit or near today? | RDS/Aurora sizing; connection pooling (RDS Proxy) | Other Prod-ready | Yes
Q102 | High-Level Application Portfolio Review | Scalability | (any app / general) | App Owner | Is multi-tenancy a factor (per-tenant isolation, noisy-neighbor, per-tenant scaling)? | Isolation model; sizing | Other Prod-ready | Yes
Q103 | High-Level Application Portfolio Review | Traffic & Load | (any app / general) | Ops/SRE | What is the request volume: average and PEAK requests/sec (or per minute) for this app's key endpoints? | ECS task count / Fargate sizing; API GW limits | Other Prod-ready | Yes
Q104 | High-Level Application Portfolio Review | Traffic & Load | (any app / general) | Ops/SRE | What is the daily/weekly traffic SHAPE (steady, business-hours spike, batch burst, overnight)? | Autoscaling policy design; scheduled scaling | Other Prod-ready | Yes
Q105 | High-Level Application Portfolio Review | Traffic & Load | (any app / general) | Ops/SRE | What is the peak-to-average ratio and how fast does traffic ramp (seconds vs minutes)? | Scale-out speed; warm pool / provisioned concurrency | Other Prod-ready | Yes
Q106 | High-Level Application Portfolio Review | Traffic & Load | (any app / general) | App Owner | Are there known/announced events (campaigns, quarter-end, market open) that multiply load? By how much? | Capacity headroom; scheduled scaling | Other Prod-ready | Yes
Q107 | High-Level Application Portfolio Review | Traffic & Load | (any app / general) | Integration | Is there rate limiting / throttling in place today (APIM policies, per-client quotas)? What limits? | API Gateway usage plans / throttle mapping | Other Prod-ready | Yes
Q108 | High-Level Application Portfolio Review | Traffic & Load | (any app / general) | Integration | Do any downstream/partner systems impose rate limits we must respect (calls/sec, daily quota)? | Backpressure; SQS buffering; retry design | Other Prod-ready | Yes
Q109 | High-Level Application Portfolio Review | Traffic & Load | (any app / general) | Ops/SRE | What happens today when limits are exceeded (429s, queueing, drop, retry)? Expected behavior on AWS? | Throttle/retry semantics; DLQ design | Other Prod-ready | Yes
Q110 | High-Level Application Portfolio Review | Traffic & Load | (any app / general) | App Owner | Are there bursty/async workloads better served by queue+worker than always-on compute? | SQS+ECS/Lambda vs always-on; cost | Other Prod-ready | Yes
Q111 | High-Level Application Portfolio Review | Traffic & Load | (any app / general) | Ops/SRE | What is the request SIZE profile (typical and max payload) and any large-upload/download paths? | ALB/API GW payload limits; S3 offload | Other Prod-ready | Yes
Q112 | High-Level Application Portfolio Review | Traffic & Load | (any app / general) | Ops/SRE | What concurrency does the app sustain (concurrent users / in-flight requests) at peak? | Connection limits; thread/worker sizing | Other Prod-ready | Yes
AWS LZ & Shared Infrastructure Foundation
Q113 | AWS LZ & Shared Infrastructure Foundation | AWS Access | N/A |  | What AWS account/LZ/Radius access does VR need to validate the environment and migration readiness? |  | Core
Q114 | AWS LZ & Shared Infrastructure Foundation | Discovery Access | All |  | What Azure, application, repository, monitoring and documentation access will VR need for discovery? |  | Core
Q115 | AWS LZ & Shared Infrastructure Foundation | Domain-specific questions | N/A |  | How do digital applications interact with the ingress/egress solution? How do they reach the internet and non-Azure areas of the internal network? |  | Core
Q116 | AWS LZ & Shared Infrastructure Foundation | Domain-specific questions | N/A |  | What is the process for raising FW requests, how long does it take, and does it usually work first time? |  | Core
Q117 | AWS LZ & Shared Infrastructure Foundation | Domain-specific questions | N/A |  | What observability tools are currently used by Parametric? Native Azure, third-party, or a mix? |  | Core
Q118 | AWS LZ & Shared Infrastructure Foundation | Domain-specific questions | N/A |  | What is the logging landscape at Morgan Stanley? Native AWS, third-party, or a mix? |  | Core
Q119 | AWS LZ & Shared Infrastructure Foundation | ETS / connectivity | N/A |  | What ETS/network capabilities and dependencies are required to connect Digital workloads, on-prem, AWS/shared services and external systems? |  | Core
Q120 | AWS LZ & Shared Infrastructure Foundation | Hybrid Operations | (any app / general) | Ops/SRE | During the hybrid period, who owns incident response for this app (Parametric, VR, shared)? | Operating model; RACI | Other Prod-ready | Yes
Q121 | AWS LZ & Shared Infrastructure Foundation | Hybrid Operations | (any app / general) | Ops/SRE | Will monitoring be split (Azure + AWS) during migration, and how are alerts correlated? | Observability during hybrid | Other Prod-ready | Yes
Q122 | AWS LZ & Shared Infrastructure Foundation | Hybrid Operations | (any app / general) | Network | What is the expected lifetime of hybrid connectivity (DX/VPN) and its cost owner? | Hybrid duration; cost | Other Prod-ready | No
Q123 | AWS LZ & Shared Infrastructure Foundation | Hybrid Operations | (any app / general) | Security/IAM | During hybrid, how is identity kept consistent across Azure AD / on-prem AD / Okta / AWS IAM? | Federation continuity | Other Prod-ready | No
Q124 | AWS LZ & Shared Infrastructure Foundation | Hybrid Operations | (any app / general) | App Owner | Is there a 'no new feature on old platform' freeze policy once migration starts? | Change control; risk | Other Prod-ready | Yes
Q125 | AWS LZ & Shared Infrastructure Foundation | IAC | N/A |  | Which Terraform scripts or infrastructure patterns are expected for the Digital workloads? |  | Core
Q126 | AWS LZ & Shared Infrastructure Foundation | LZ & Foundation capabilities | N/A |  | What high-level capabilities are handled/owned as part of the LZ & Foundation? (account vending, SCPs, ingress/egress, IAM, etc) |  | Core
Q127 | AWS LZ & Shared Infrastructure Foundation | LZ & Foundation capabilities | N/A |  | What is the release schedule for the LZ & Foundation capabilities? |  | Core
Q128 | AWS LZ & Shared Infrastructure Foundation | LZ & Foundation capabilities | N/A |  | How do teams request changes to the LZ & Foundation? |  | Core
Q129 | AWS LZ & Shared Infrastructure Foundation | LZ & Foundation capabilities | N/A |  | What approvals are required for changes to the LZ & Foundation? |  | Core
Q130 | AWS LZ & Shared Infrastructure Foundation | Load Balancing | (any app / general) | Network | How is traffic load-balanced today (Azure LB, App Gateway, Front Door, Traffic Manager)? L4 or L7? | ALB/NLB/CloudFront/Global Accelerator mapping | Other Prod-ready | Yes
Q131 | AWS LZ & Shared Infrastructure Foundation | Load Balancing | (any app / general) | Network | Are sticky sessions / session affinity required? By what key (cookie, IP)? | ALB stickiness; statelessness refactor | Other Prod-ready | Yes
Q132 | AWS LZ & Shared Infrastructure Foundation | Load Balancing | (any app / general) | Network | What health-check endpoints/criteria determine a healthy instance today? | Target group health checks | Other Prod-ready | Yes
Q133 | AWS LZ & Shared Infrastructure Foundation | Load Balancing | (any app / general) | Network | Is TLS terminated at the LB, passed through, or re-encrypted to backend (mTLS)? | ACM; TLS policy; end-to-end encryption | Other Prod-ready | Yes
Q134 | AWS LZ & Shared Infrastructure Foundation | Load Balancing | (any app / general) | Ops/SRE | Are there long-lived connections (WebSockets, SSE, gRPC, keep-alive) or long requests? | ALB idle timeout; NLB; connection draining | Other Prod-ready | Yes
Q135 | AWS LZ & Shared Infrastructure Foundation | Load Balancing | (any app / general) | Network | What connection-draining / graceful-shutdown behavior is needed on deploy or scale-in? | Deregistration delay; zero-downtime deploy | Other Prod-ready | Yes
Q136 | AWS LZ & Shared Infrastructure Foundation | Load Balancing | (any app / general) | Network | Is global traffic routing / geo-based routing / failover routing used today? | Route 53 routing policies; Global Accelerator | Other Prod-ready | Yes
Q137 | AWS LZ & Shared Infrastructure Foundation | Load Balancing | (any app / general) | Ops/SRE | What is the max/typical number of backend instances behind the LB at peak? | Target group sizing; subnet IP capacity | Other Prod-ready | Yes
Q138 | AWS LZ & Shared Infrastructure Foundation | MS ETS / Hosting (Context) | (any app / general) | Platform / MS | Does Morgan Stanley ETS (Enhanced Technology Support) — or any VMware SDDC it operates — host or sit in the data path of the 4 apps? If not, confirm it's out of scope for this Azure->AWS migration. | Scope boundary — confirm the ETS/VMware hint is not a dependency of the 4 apps | Other Prod-ready | Yes
Q139 | AWS LZ & Shared Infrastructure Foundation | Network | (any app / general) | Network | What VNet/subnets and NSGs does the app live in today? Any private endpoints? | VPC/subnet design | Other Prod-ready | Yes
Q140 | AWS LZ & Shared Infrastructure Foundation | Network | (any app / general) | Network | What inbound/outbound ports and protocols does the app require? | Security group design | Other Prod-ready | Yes
Q141 | AWS LZ & Shared Infrastructure Foundation | Network | (any app / general) | Network | Is there a dependency on ExpressRoute / site-to-site VPN to on-prem? | Direct Connect / TGW sizing | Other Prod-ready | Yes
Q142 | AWS LZ & Shared Infrastructure Foundation | Network | (any app / general) | Network | What are the latency sensitivities between app and its DB / dependencies? | Co-location; wave grouping | Other Prod-ready | Yes
Q143 | AWS LZ & Shared Infrastructure Foundation | Network | (any app / general) | Network | What DNS zones/records does the app rely on (public + private)? TTLs? | Route 53 cutover plan | Other Prod-ready | Yes
Q144 | AWS LZ & Shared Infrastructure Foundation | Network | (any app / general) | Network | Any fixed egress IP requirements (partner allow-lists, firewall rules)? | NAT GW / EIP; partner coordination | Other Prod-ready | Yes
Q145 | AWS LZ & Shared Infrastructure Foundation | Network | (any app / general) | Network | Is traffic fronted by Akamai / WAF today? What rules? | Red Zone ingress parity | Other Prod-ready | Yes
Q146 | AWS LZ & Shared Infrastructure Foundation | Network | (any app / general) | Network | Bandwidth required for data migration (DB + blob) and is Direct Connect capacity sufficient? | Migration logistics; Snowball? | Other Prod-ready | No
Q147 | AWS LZ & Shared Infrastructure Foundation | Network Detail | (any app / general) | Network | Are there static/whitelisted source IPs that partners or firewalls depend on (ingress or egress)? | EIP/NAT GW; partner re-whitelisting; DC-exit | Other Prod-ready | Yes
Q148 | AWS LZ & Shared Infrastructure Foundation | Network Detail | (any app / general) | Network | Is there any asymmetric routing, NAT, proxy, or hairpin traffic pattern today? | VPC routing design; endpoint policies | Other Prod-ready | No
Q149 | AWS LZ & Shared Infrastructure Foundation | Network Detail | (any app / general) | Network | Are there private endpoints / service endpoints to Azure PaaS that need AWS PrivateLink equivalents? | VPC endpoints / PrivateLink design | Other Prod-ready | Yes
Q150 | AWS LZ & Shared Infrastructure Foundation | Network Detail | (any app / general) | Network | What is the east-west (service-to-service) traffic volume and does it cross AZ/region today? | AZ affinity; cross-AZ data cost | Other Prod-ready | Yes
Q151 | AWS LZ & Shared Infrastructure Foundation | Network Detail | (any app / general) | Network | Are there MTU, jumbo-frame, or packet-size sensitivities (VPN, legacy protocols)? | VPN/DX MTU; path MTU issues | Other Prod-ready | No
Q152 | AWS LZ & Shared Infrastructure Foundation | Network Detail | (any app / general) | Network | Any multicast, broadcast, or non-TCP/UDP protocols in use (legacy, clustering)? | AWS protocol support gaps; redesign | Other Prod-ready | No
Q153 | AWS LZ & Shared Infrastructure Foundation | Network Detail | (any app / general) | Network | What outbound internet dependencies exist (package repos, APIs, telemetry) and their volume? | NAT GW sizing/cost; egress design | Other Prod-ready | Yes
Q154 | AWS LZ & Shared Infrastructure Foundation | Network Detail | (any app / general) | Network | Are there known network pain points today (latency spikes, saturation, DNS flakiness, retries)? | Avoid porting the problem; design fix | Other Prod-ready | Yes
Q155 | AWS LZ & Shared Infrastructure Foundation | Network Detail | (any app / general) | Network | What DNS resolution patterns exist (split-horizon, conditional forwarders to on-prem)? | Route 53 Resolver; hybrid DNS | Other Prod-ready | Yes
Q156 | AWS LZ & Shared Infrastructure Foundation | Observability | (any app / general) | Observability | Where do logs go today (Log Analytics workspace, App Insights, Splunk, DataDog)? | CloudWatch/X-Ray/DataDog/Splunk routing | Other Prod-ready | Yes
Q157 | AWS LZ & Shared Infrastructure Foundation | Observability | (any app / general) | Observability | If logs go to Splunk/DataDog on-prem or SaaS — can AWS ship to the EXISTING platform over connectivity? | Splunk rule: Wave-0 connectivity vs migrate | Other Prod-ready | No
Q158 | AWS LZ & Shared Infrastructure Foundation | Observability | (any app / general) | Observability | What metrics/alarms exist and who is paged? What are the SLOs? | CloudWatch alarms; ops readiness | Other Prod-ready | Yes
Q159 | AWS LZ & Shared Infrastructure Foundation | Observability | (any app / general) | Observability | Is there distributed tracing today? Instrumented how? | X-Ray / DataDog APM | Other Prod-ready | Yes
Q160 | AWS LZ & Shared Infrastructure Foundation | Observability | (any app / general) | Observability | What dashboards must exist on day 1 after cutover? | Observability gate | Other Prod-ready | Yes
Q161 | AWS LZ & Shared Infrastructure Foundation | Operational management | N/A |  | What are the specifics of account vending? How long to get them vended and what does the vended environment come with? |  | Core
Q162 | AWS LZ & Shared Infrastructure Foundation | Operational management | N/A |  | As Cloud Infrastructure Migration Engineers, what will our access pattern be to AWS accounts? Console and CLI access? |  | Core
Q163 | AWS LZ & Shared Infrastructure Foundation | Platform | N/A |  | How do Red Zone, Radius and other shared AWS capabilities relate to the Digital workloads, and which will Digital consume? |  | Core
Q164 | AWS LZ & Shared Infrastructure Foundation | Platform Readiness | N/A |  | Which LZ/Foundation capabilities are available today, which are planned, and which have dependencies/timelines affecting sequencing? |  | Core
Q165 | AWS LZ & Shared Infrastructure Foundation | Security & IAM | (any app / general) | Security/IAM | How do users authenticate (Okta SSO, Azure AD, local)? Any Azure AD app registrations? | Okta/IAM federation | Other Prod-ready | Yes
Q166 | AWS LZ & Shared Infrastructure Foundation | Security & IAM | (any app / general) | Security/IAM | How do services authenticate to Azure resources (Managed Identity, service principals, conn strings)? | IAM roles; secrets refactor | Other Prod-ready | Yes
Q167 | AWS LZ & Shared Infrastructure Foundation | Security & IAM | (any app / general) | Security/IAM | What secrets/certs live in Key Vault and how are they referenced? | Secrets Manager + ACM migration | Other Prod-ready | Yes
Q168 | AWS LZ & Shared Infrastructure Foundation | Security & IAM | (any app / general) | Security/IAM | What RBAC roles / groups govern access and where are they defined? | IAM / Okta RBAC mapping | Other Prod-ready | Yes
Q169 | AWS LZ & Shared Infrastructure Foundation | Security & IAM | (any app / general) | Security/IAM | Any data classification (PII, PCI, confidential) and encryption requirements (at rest/in transit)? | KMS; compliance gate | Other Prod-ready | Yes
Q170 | AWS LZ & Shared Infrastructure Foundation | Security & IAM | (any app / general) | Security/IAM | Does the app have a Morgan Stanley SecArch approval dependency or control baseline to meet? | Radius blueprint conformance | Other Prod-ready | No
Q171 | AWS LZ & Shared Infrastructure Foundation | Security & IAM | (any app / general) | Security/IAM | Are there security scanners / endpoint agents that must be present (Qualys, CrowdStrike, etc.)? | Agent install in AMI/task; DC-exit | Other Prod-ready | Yes
Q172 | AWS LZ & Shared Infrastructure Foundation | Security & IAM | (any app / general) | Security/IAM | What audit/logging obligations apply (who accessed what, retention period)? | CloudTrail; log retention | Other Prod-ready | Yes
Service Onboarding Framework
Q173 | Service Onboarding Framework | AWS service onboarding | N/A |  | For a given AWS service, what is the submission/request process? |  | Core
Q174 | Service Onboarding Framework | AWS service onboarding | N/A |  | For a given AWS service, how many rounds of review occur? |  | Core
Q175 | Service Onboarding Framework | AWS service onboarding | N/A |  | For a given AWS service, what is the typical duration between request and fulfillment? |  | Core
Q176 | Service Onboarding Framework | AWS service onboarding | N/A |  | For a given AWS service, are there standard security and compliance considerations that apply to all services? |  | Core
Q177 | Service Onboarding Framework | AWS service onboarding | N/A |  | For a given AWS service, what approvals are required? |  | Core
Q178 | Service Onboarding Framework | AWS service onboarding | N/A |  | For a given AWS service, how does the handoff work once it is approved? |  | Core
Q179 | Service Onboarding Framework | DevOps & CI/CD | (any app / general) | DevOps/CICD | How is the app built and deployed today (Azure DevOps, GitHub Actions, Jenkins)? Pipeline location? | CI/CD migration; Jenkins disposition | Other Prod-ready | Yes
Q180 | Service Onboarding Framework | DevOps & CI/CD | (any app / general) | DevOps/CICD | Where is source code hosted and who has access? | Repo access; pipeline rebuild | Other Prod-ready | Yes
Q181 | Service Onboarding Framework | DevOps & CI/CD | (any app / general) | DevOps/CICD | Is infrastructure defined as code today? If so, in what (ARM/Bicep/Terraform)? | Terraform L1/L2/L3 reuse | Other Prod-ready | Yes
Q182 | Service Onboarding Framework | DevOps & CI/CD | (any app / general) | DevOps/CICD | What artifact registries are used (ACR, npm, NuGet)? Migrate to ECR? | ECR; artifact pipeline | Other Prod-ready | Yes
Q183 | Service Onboarding Framework | DevOps & CI/CD | (any app / general) | DevOps/CICD | What is the release cadence and is a code freeze feasible during cutover? | Cutover window; freeze | Other Prod-ready | Yes
Q184 | Service Onboarding Framework | DevOps & CI/CD | (any app / general) | DevOps/CICD | Does the app have automated tests (unit/integration/smoke) usable for migration validation? | Testing gate | Other Prod-ready | Yes
Q185 | Service Onboarding Framework | Lead Time | N/A |  | Which onboarding activities commonly cause delay or require lead time? |  | Core
Q186 | Service Onboarding Framework | Recent onboarding example | N/A |  | Which recently onboarded service can we use as an example to walk through? |  | Core
Q187 | Service Onboarding Framework | Recent onboarding example | N/A |  | What documentation did that service provide during onboarding? |  | Core
Q188 | Service Onboarding Framework | Recent onboarding example | N/A |  | How long did the onboarding process take for that service? |  | Core
Q189 | Service Onboarding Framework | Recent onboarding example | N/A |  | Which onboarding activities are automated and which require manual requests or approvals? |  | Core
Q190 | Service Onboarding Framework | Workload onboarding | N/A |  | How do workloads onboard to AWS? |  | Core
Application Dispositioning Framework
Q191 | Application Dispositioning Framework | Approval | All |  | Who reviews and approves the resulting application disposition? |  | Core
Q192 | Application Dispositioning Framework | Compliance | (any app / general) | Security/IAM | What data retention and legal-hold obligations apply to this app's data? | Retention; S3 lifecycle; DC-exit | Other Prod-ready | Yes
Q193 | Application Dispositioning Framework | Compliance | (any app / general) | Security/IAM | Are there data residency constraints that fix region to us-west-2 / us-east-1? | Region strategy | Other Prod-ready | Yes
Q194 | Application Dispositioning Framework | Compliance | (any app / general) | App Owner | Are there audit evidence requirements for the migration itself (who approved, when)? | Audit trail; governance | Other Prod-ready | Yes
Q195 | Application Dispositioning Framework | Compliance | (any app / general) | Security/IAM | Does decommissioning the Azure resources require certified data destruction? | DC-exit; compliance | Other Prod-ready | No
Q196 | Application Dispositioning Framework | Constraints | Each App |  | What technical, business, regulatory or platform constraints could influence disposition? |  | Core
Q197 | Application Dispositioning Framework | Cost & Licensing | (any app / general) | App Owner | What SQL Server / Windows / third-party licenses apply, and are they BYOL or Azure-included? | RDS licensing (LI vs BYOL); cost | Other Prod-ready | Yes
Q198 | Application Dispositioning Framework | Cost & Licensing | (any app / general) | App Owner | Are there software products that are licensed per-core or per-socket that affect right-sizing? | Right-sizing; cost model | Other Prod-ready | Yes
Q199 | Application Dispositioning Framework | Cost & Licensing | (any app / general) | Ops/SRE | What are current Azure monthly costs for this app (compute, DB, storage, egress)? | TCO baseline; savings case | Other Prod-ready | Yes
Q200 | Application Dispositioning Framework | Cost & Licensing | (any app / general) | App Owner | Any committed-use/reserved commitments on Azure that constrain decommission timing? | DC-exit timing; cost | Other Prod-ready | Yes
Q201 | Application Dispositioning Framework | Cost & Licensing | (any app / general) | Integration | Are there data-egress-heavy flows that will incur AWS transfer cost or need redesign? | Cost; architecture | Other Prod-ready | No
Q202 | Application Dispositioning Framework | Decision criteria | N/A |  | What criteria determine the target disposition (EVS, Radius, EC2, SaaS or retire)? |  | Core
Q203 | Application Dispositioning Framework | Decision criteria | N/A |  | Who makes and approves the final disposition decision? |  | Core
Q204 | Application Dispositioning Framework | Dependencies/Disposition | N/A |  | How are application dependencies and shared-service dependencies incorporated into the disposition decision? |  | Core
Q205 | Application Dispositioning Framework | Dependency Disposition | (any app / general) | Integration | For EACH shared service used (AD, DNS, Splunk, Jenkins, SMTP, SFTP, ServiceNow, backup, scanners): does it MUST-move-before? | Engine input: must-move-before | Other Prod-ready | No
Q206 | Application Dispositioning Framework | Dependency Disposition | (any app / general) | Integration | For EACH shared service: can it STAY on-prem/Azure while this app moves? | Engine input: can-remain | Other Prod-ready | No
Q207 | Application Dispositioning Framework | Dependency Disposition | (any app / general) | Integration | For EACH shared service: must it move WITH this app (same cutover)? | Engine input: must-move-with (move group) | Other Prod-ready | No
Q208 | Application Dispositioning Framework | Dependency Disposition | (any app / general) | Integration | For EACH shared service: can it move LATER than this app? | Engine input: can-move-later | Other Prod-ready | No
Q209 | Application Dispositioning Framework | Dependency Disposition | (any app / general) | Integration | For EACH shared service: is it ONLY a DC-exit blocker (keep until the very end)? | Engine input: DC-exit-blocker | Other Prod-ready | No
Q210 | Application Dispositioning Framework | Dependency Disposition | (any app / general) | DBA | Does this app share a database with another app such that they must cut over together? | Engine input: move-group formation | Other Prod-ready | Yes
Q211 | Application Dispositioning Framework | Dependency Disposition | (any app / general) | Ops/SRE | Is this app part of a batch/job chain where ordering with other apps matters at cutover? | Engine input: sequencing constraint | Other Prod-ready | No
Q212 | Application Dispositioning Framework | Dependency Disposition | (any app / general) | Integration | Does any OTHER app depend on this app being migrated first (reverse prerequisite)? | Engine input: must-move-before (reverse) | Other Prod-ready | No
Q213 | Application Dispositioning Framework | Disposition Criteria | All |  | What criteria determine whether a workload is rehosted, replatformed, re-engineered or handled through another approved pattern? |  | Core
Q214 | Application Dispositioning Framework | Documentation & Knowledge | (any app / general) | App Owner | Where is current architecture / runbook / network documentation, and is it accurate? | Discovery accuracy; ops handover | Other Prod-ready | Yes
Q215 | Application Dispositioning Framework | Documentation & Knowledge | (any app / general) | App Owner | Who holds tribal knowledge not captured in docs (key-person risk)? | RAID risk; interview target | Other Prod-ready | Yes
Q216 | Application Dispositioning Framework | Documentation & Knowledge | (any app / general) | Ops/SRE | What CMDB/asset system tracks this app and will it be updated post-migration? | CMDB update; ops | Other Prod-ready | Yes
Q217 | Application Dispositioning Framework | Existing AWS work/baseline | N/A |  | What prior AWS or MS application pre-disposition assessments already exist, and which findings are inputs to this framework? |  | Core
Q218 | Application Dispositioning Framework | Platform readiness | N/A |  | How does readiness of the target platform or required shared services affect the disposition decision? |  | Core
Q219 | Application Dispositioning Framework | Prior dispositions | N/A |  | What did previous Application Dispositions consist of, and in what order did they unfold? Was it kicked off formally, or did it begin with SecArch? |  | Core
Q220 | Application Dispositioning Framework | Prior dispositions | N/A |  | How much do Application Dispositions vary from one application to another, and what drives the variation? |  | Core
Q221 | Application Dispositioning Framework | Prior dispositions | N/A |  | Can we walk through one or two completed Application Dispositions as examples? |  | Core
Q222 | Application Dispositioning Framework | Process | N/A |  | Are there steps that always must happen, such as SecArch review? |  | Core
Q223 | Application Dispositioning Framework | Process | N/A |  | If the Application Disposition process is documented, where can we get that documentation and who owns it? |  | Core
Q224 | Application Dispositioning Framework | Teams involved | N/A |  | Beyond SecArch, what teams typically need to be involved? |  | Core
Q225 | Application Dispositioning Framework | Teams involved | N/A |  | At what point in the process is each team engaged, and what does each team provide or decide? |  | Core
Q226 | Application Dispositioning Framework | Timing and outcomes | N/A |  | How long does a typical Application Disposition take from start to finish? |  | Core
Q227 | Application Dispositioning Framework | Timing and outcomes | N/A |  | How are approved dispositions revisited or changed when scope or priorities change? |  | Core
Q228 | Application Dispositioning Framework | Tooling and data | N/A |  | What information must be available before a disposition can start (current/target architecture, network flows, dependencies)? |  | Core
Q229 | Application Dispositioning Framework | Validation | N/A |  | What would constitute a successful validation of the disposition framework on the representative Digital applications? |  | Core
Data / DB Inventory Deep Dive
Q230 | Data / DB Inventory Deep Dive | Azure coupling | N/A |  | What Azure-specific dependencies exist around the data platform (Managed Identity, Key Vault, Private Endpoints, Data Factory, Synapse, Functions, Storage)? |  | Core
Q231 | Data / DB Inventory Deep Dive | Compatibility | N/A |  | What DB-specific features or cross-database dependencies could constrain migration (stored procs, jobs, linked servers, extensions, replication, triggers, shared schemas)? |  | Core
Q232 | Data / DB Inventory Deep Dive | Data | (any app / general) | DBA | Which databases does this app use (Azure SQL DB, Managed Instance, Elastic Pool member)? | RDS target; DMS planning | Other Prod-ready | Yes
Q233 | Data / DB Inventory Deep Dive | Data | (any app / general) | DBA | Is the database SHARED with other applications? If so, which ones? | MOVE GROUP formation (critical!) | Other Prod-ready | Yes
Q234 | Data / DB Inventory Deep Dive | Data | (any app / general) | DBA | What is the database size (GB) and daily change/transaction volume? | DMS duration; data-volume score | Other Prod-ready | Yes
Q235 | Data / DB Inventory Deep Dive | Data | (any app / general) | DBA | What SQL Server version/compat level and are there cross-DB queries, linked servers, SQL Agent jobs? | RDS vs RDS Custom; migration risk | Other Prod-ready | Yes
Q236 | Data / DB Inventory Deep Dive | Data | (any app / general) | DBA | Are there CLR assemblies, Service Broker, FileStream, or features unsupported on RDS for SQL Server? | RDS feasibility; re-architect flag | Other Prod-ready | Yes
Q237 | Data / DB Inventory Deep Dive | Data | (any app / general) | DBA | What is the acceptable data-loss window (RPO) for this database? | RPO; replication strategy | Other Prod-ready | Yes
Q238 | Data / DB Inventory Deep Dive | Data | (any app / general) | DBA | Can we use AWS DMS with CDC for near-zero-downtime, or is a backup/restore cutover acceptable? | Cutover method; downtime | Other Prod-ready | Yes
Q239 | Data / DB Inventory Deep Dive | Data | (any app / general) | DBA | Are there Elastic Pool co-tenants that must be split or kept together on RDS? | Move group; consolidation | Other Prod-ready | Yes
Q240 | Data / DB Inventory Deep Dive | Data | (any app / general) | DBA | What are the current DB HA/DR settings (geo-replication, failover groups, backup retention)? | Multi-AZ; backup design | Other Prod-ready | Yes
Q241 | Data / DB Inventory Deep Dive | Data | (any app / general) | DBA | Does the app use any NoSQL / MongoDB / Cosmos DB / Redis-persisted data? | ElastiCache / DocumentDB / MongoDB Atlas | Other Prod-ready | Yes
Q242 | Data / DB Inventory Deep Dive | Data | (any app / general) | DBA | What file/blob storage does the app read/write (Azure Blob, Files)? Size and access pattern? | S3 / EFS target; move group | Other Prod-ready | Yes
Q243 | Data / DB Inventory Deep Dive | Data | (any app / general) | DBA | Are there batch/ETL jobs via Data Factory that touch this app's data? | Glue/Step Functions re-architect | Other Prod-ready | Yes
Q244 | Data / DB Inventory Deep Dive | Data & Analytics | (any app / general) | DBA | For each data store, is the workload TRANSACTIONAL (OLTP) or ANALYTICAL (OLAP/reporting)? Or mixed (HTAP)? | RDS/Aurora vs Redshift/Athena target; HUGE design driver | Other Prod-ready | Yes
Q245 | Data / DB Inventory Deep Dive | Data & Analytics | (any app / general) | DBA | Are heavy reports/analytics run against the PRODUCTION transactional DB today (contention risk)? | Read replica / offload to Redshift/Athena | Other Prod-ready | Yes
Q246 | Data / DB Inventory Deep Dive | Data & Analytics | (any app / general) | DBA | What is the read:write ratio and are reads scalable via replicas? | Aurora read replicas; caching | Other Prod-ready | Yes
Q247 | Data / DB Inventory Deep Dive | Data & Analytics | (any app / general) | DBA | What data warehouse / BI / reporting platform exists (Synapse, Power BI, Tableau)? Fed how? | Redshift/QuickSight; pipeline redesign | Other Prod-ready | Yes
Q248 | Data / DB Inventory Deep Dive | Data & Analytics | (any app / general) | DBA | What ETL/ELT pipelines (Data Factory) move/transform data, their schedules and SLAs? | Glue + Step Functions re-architect; SLA | Other Prod-ready | Yes
Q249 | Data / DB Inventory Deep Dive | Data & Analytics | (any app / general) | DBA | Is there streaming/real-time analytics (Event Hubs/Stream Analytics) vs batch? Latency need? | Kinesis/Flink vs batch Glue | Other Prod-ready | Yes
Q250 | Data / DB Inventory Deep Dive | Data & Analytics | (any app / general) | DBA | What are data volumes & growth rate per store (hot/warm/cold), and retention tiers? | S3 tiering; Redshift sizing; lifecycle | Other Prod-ready | Yes
Q251 | Data / DB Inventory Deep Dive | Data & Analytics | (any app / general) | DBA | Are there large joins/aggregations/scans that drive sizing (analytical heavy lifting)? | Columnar store (Redshift) vs row store | Other Prod-ready | Yes
Q252 | Data / DB Inventory Deep Dive | Data & Analytics | (any app / general) | DBA | What data-freshness SLA do consumers need (real-time, hourly, daily)? | Streaming vs batch; pipeline design | Other Prod-ready | Yes
Q253 | Data / DB Inventory Deep Dive | Data & Analytics | (any app / general) | DBA | Is there CDC / change-data-capture feeding downstream systems or lakes today? | DMS CDC; Kinesis; lake hydration | Other Prod-ready | Yes
Q254 | Data / DB Inventory Deep Dive | Data & Analytics | (any app / general) | DBA | Are there data-quality, reconciliation, or master-data processes that must be preserved? | Glue DQ; pipeline parity | Other Prod-ready | Yes
Q255 | Data / DB Inventory Deep Dive | Data & Analytics | (any app / general) | DBA | Is there a data lake / blob-based analytics today? Format (Parquet/CSV), partitioning? | S3 + Athena/Glue catalog; Lake Formation | Other Prod-ready | Yes
Q256 | Data / DB Inventory Deep Dive | Data Migration Logistics | (any app / general) | DBA | Total data to move for this app (DB + blob + files) in GB/TB? | Migration logistics; DX vs Snowball | Other Prod-ready | Yes
Q257 | Data / DB Inventory Deep Dive | Data Migration Logistics | (any app / general) | Network | Given Direct Connect capacity, is online transfer feasible in the window, or is offline (Snowball) needed? | Transfer method; timeline | Other Prod-ready | No
Q258 | Data / DB Inventory Deep Dive | Data Migration Logistics | (any app / general) | DBA | Is there data that must be masked/anonymized for non-prod targets? | Data handling; compliance | Other Prod-ready | Yes
Q259 | Data / DB Inventory Deep Dive | Data Migration Logistics | (any app / general) | DBA | Are there large historical/cold datasets that can go to S3 Glacier rather than hot storage? | Cost; S3 tiering | Other Prod-ready | Yes
Q260 | Data / DB Inventory Deep Dive | Data Migration Logistics | (any app / general) | DBA | What data reconciliation / checksum method proves the migration is complete and correct? | Validation gate; go/no-go | Other Prod-ready | Yes
Q261 | Data / DB Inventory Deep Dive | Data Migration Logistics | (any app / general) | Integration | Are there in-flight transactions or event backlogs that must drain before cutover? | Cutover sequencing | Other Prod-ready | No
Q262 | Data / DB Inventory Deep Dive | Data engineering | N/A |  | What ETL/ELT, reporting, BI, batch, CDC or streaming workloads depend on these stores, and what are their schedules and freshness requirements? |  | Core
Q263 | Data / DB Inventory Deep Dive | Database inventory | N/A |  | What databases/data stores support SMAP, IPORT, IMAT and .com today? Include engine, version, hosting model and environment. |  | Core
Q264 | Data / DB Inventory Deep Dive | HA / DR | N/A |  | What availability, RTO/RPO, backup/restore and DR requirements must the AWS target satisfy, and what recovery capabilities have been tested? |  | Core
Q265 | Data / DB Inventory Deep Dive | Inventory & app mapping | N/A |  | What data stores support each application, which apps use them, which are shared, and which are systems of record vs reporting/cache/analytics? |  | Core
Q266 | Data / DB Inventory Deep Dive | Migration constraints | N/A |  | Given DB size, change rate, downtime tolerance and RPO, what migration approaches are feasible (backup/restore, DMS full-load + CDC, replication, export/import)? |  | Core
Q267 | Data / DB Inventory Deep Dive | Performance | N/A |  | What are current DB performance characteristics and pain points (p95/p99 latency, IOPS/throughput, locking, connection pressure, slow reporting)? |  | Core
Q268 | Data / DB Inventory Deep Dive | Security & connectivity | N/A |  | How do apps/users authenticate to the DB, what encryption requirements apply, and what private-network/firewall connectivity is required? |  | Core
Q269 | Data / DB Inventory Deep Dive | Target / exit | N/A |  | What MS-approved AWS database patterns apply, and what prevents the Azure database from being decommissioned after migration? |  | Core
Q270 | Data / DB Inventory Deep Dive | Validation & rollback | N/A |  | How will migrated data be validated, and if users write after cutover, how will rollback/reverse sync preserve consistency? |  | Core
Q271 | Data / DB Inventory Deep Dive | Wave sequencing | N/A |  | Can the application migrate while its DB stays in Azure/on-prem? Can the DB move first? Or must DB and apps move together? |  | Core
Q272 | Data / DB Inventory Deep Dive | Workload characteristics | N/A |  | For each major store, is the workload OLTP, OLAP/analytics, mixed, cache/search or lake, and what are its load characteristics (read/write ratio, peak TPS, connections, size, growth)? |  | Core
Program Roadmap / Wave Plan
Q273 | Program Roadmap / Wave Plan | Cutover | (any app / general) | App Owner | What is the preferred cutover approach: big-bang, blue/green, or phased? | Cutover design | Other Prod-ready | No
Q274 | Program Roadmap / Wave Plan | Cutover | (any app / general) | App Owner | What validation/smoke tests prove the app is healthy post-cutover? | Go/no-go criteria | Other Prod-ready | Yes
Q275 | Program Roadmap / Wave Plan | Cutover | (any app / general) | App Owner | What is the rollback plan and how long does rollback take? | Rollback difficulty score | Other Prod-ready | No
Q276 | Program Roadmap / Wave Plan | Cutover | (any app / general) | DBA | For the database, is bidirectional sync needed for rollback safety? | DMS reverse; rollback | Other Prod-ready | No
Q277 | Program Roadmap / Wave Plan | Cutover | (any app / general) | Network | What DNS/traffic-shift mechanism is used at cutover and what is the TTL? | Cutover mechanics | Other Prod-ready | No
Q278 | Program Roadmap / Wave Plan | Cutover | (any app / general) | App Owner | Who are the go/no-go approvers and what is the escalation path? | Cutover governance | Other Prod-ready | Yes
Q279 | Program Roadmap / Wave Plan | Cutover | (any app / general) | App Owner | Is there a 'cutover rehearsal' / dress-rehearsal expectation before the real cutover? | Cutover plan; schedule | Other Prod-ready | Yes
Q280 | Program Roadmap / Wave Plan | Cutover | (any app / general) | Ops/SRE | What hypercare period and staffing is expected post-cutover? | Hypercare plan; ops readiness | Other Prod-ready | Yes
Q281 | Program Roadmap / Wave Plan | Cutover | (any app / general) | App Owner | Is a parallel-run (old + new live simultaneously) required for assurance? | Cutover method; cost | Other Prod-ready | No
Q282 | Program Roadmap / Wave Plan | Dependency validation | N/A |  | Does our proposed dependency map and move-group structure correctly represent what must move together? What dependencies are missing? |  | Core
Q283 | Program Roadmap / Wave Plan | Final validation | N/A |  | What assumptions/open decisions remain, what residual services prevent DC exit, and does Parametric/MS agree with the sequence? |  | Core
Q284 | Program Roadmap / Wave Plan | Governance | N/A |  | What SecArch, architecture, CAB, service-onboarding, business or operational approvals are required before each wave? |  | Core
Q285 | Program Roadmap / Wave Plan | Operations | (any app / general) | Ops/SRE | Who operates the app day-to-day and what runbooks exist? | Ops readiness; handover | Other Prod-ready | Yes
Q286 | Program Roadmap / Wave Plan | Operations | (any app / general) | Ops/SRE | What is the current patching / maintenance process? | Managed services reduce toil | Other Prod-ready | Yes
Q287 | Program Roadmap / Wave Plan | Operations | (any app / general) | Ops/SRE | Are there batch schedules / job chains (and sequence dependencies between apps)? | Batch chain = move group; wave | Other Prod-ready | No
Q288 | Program Roadmap / Wave Plan | Operations | (any app / general) | Ops/SRE | What support tooling is used (ServiceNow, PagerDuty)? Integration points? | ServiceNow disposition; DC-exit | Other Prod-ready | Yes
Q289 | Program Roadmap / Wave Plan | Operations | (any app / general) | Ops/SRE | What manual steps exist in a typical deploy or recovery? | Automation gap; cutover risk | Other Prod-ready | Yes
Q290 | Program Roadmap / Wave Plan | Pilot | N/A |  | Which workload should prove the migration pattern first, and what must the pilot demonstrate before later waves? |  | Core
Q291 | Program Roadmap / Wave Plan | Platform readiness | N/A |  | What are the actual readiness dates or blockers for LZ, Radius/Red Zone, networking, security, IAM, observability, CI/CD? |  | Core
Q292 | Program Roadmap / Wave Plan | Prerequisites / hybrid | N/A |  | For each move group, what must be ready before it moves, what can remain hybrid temporarily, and what is only a final DC-exit dependency? |  | Core
Q293 | Program Roadmap / Wave Plan | Sequencing | N/A |  | Why can't each proposed move group move one wave earlier, and which groups can run in parallel vs serial? |  | Core
Q294 | Program Roadmap / Wave Plan | Technical constraints | N/A |  | Do database/data, traffic, performance, latency, batch, scaling or rollback requirements require changing any proposed wave? |  | Core
Q295 | Program Roadmap / Wave Plan | Testing & Validation | (any app / general) | DevOps/CICD | What test suites exist (unit/integration/e2e/perf) and can they run against the AWS target? | Validation gate | Other Prod-ready | Yes
Q296 | Program Roadmap / Wave Plan | Testing & Validation | (any app / general) | App Owner | What are the key user journeys that MUST be validated post-cutover? | Smoke test definition; go/no-go | Other Prod-ready | Yes
Q297 | Program Roadmap / Wave Plan | Testing & Validation | (any app / general) | Ops/SRE | Is a performance/load baseline available to compare pre vs post migration? | Perf validation | Other Prod-ready | Yes
Q298 | Program Roadmap / Wave Plan | Testing & Validation | (any app / general) | Security/IAM | What security/pen-test or control validation must pass before go-live (SecArch)? | Security gate | Other Prod-ready | No
Q299 | Program Roadmap / Wave Plan | Testing & Validation | (any app / general) | DBA | How is data integrity validated after migration (row counts, checksums, business reconciliation)? | Data validation gate | Other Prod-ready | Yes
Q300 | Program Roadmap / Wave Plan | Timing constraints | N/A |  | What business blackouts, release freezes, SME/resource limits, vendors, partner changes or lead times constrain the roadmap? |  | Core
Q301 | Program Roadmap / Wave Plan | Wave gates | N/A |  | What must be true to enter a wave, what must be proven to exit it, and what stabilization/rollback period is required? |  | Core
Total: 301 questions — Core Discovery: 120 + Prod-Ready: 181 ( 0 duplicates removed ).

## Walkthrough & Design
Walkthrough / Design Narrative — how discovery becomes a defensible wave plan
The end-to-end design (internal review)
1. ASK by application and by domain (portfolio review) + ask the shared-platform workshops (LZ, onboarding, disposition, data, roadmap).
2. CAPTURE live, per app: the answer, plus any Risk / Dependency / Assumption / Decision-needed, with an Owner. (Nothing is left as a blank stare.)
3. DERIVE the disposition from the captured facts — two birds, one stone:
'SMAP runs on Azure SQL' -> target Amazon RDS for SQL Server (Multi-AZ)
'IMAT is .NET Framework on App Service' -> containerize to ECS Fargate; refactor flagged
'uses Azure Service Bus' -> SQS / SNS / EventBridge
4. GROUP into Move Groups = things that must move together (e.g. apps sharing one database).
5. SEQUENCE Move Groups into Waves — computed from dependencies + readiness + risk, with business criticality only as a modifier.
6. VALIDATE in the Program Roadmap workshop; residual shared services (Splunk/AD/SFTP) migrate at final DC-exit, not before.
Worked As draft — validate in workshops)
Move Group | Members | Wave | Why
MG-00 | AWS LZ / Radius / Red Zone / IAM-Okta / networking | Wave 0 — Foundation | Enabler for everything; no app can move before it.
MG-01 | SMAP (lowest-coupled portal) | Wave 1 — Prove the pattern | Standalone, low risk — proves ECS Fargate + RDS + edge path.
MG-02 | IPORT + IMAT + shared SQL | Wave 2 — Dependency group | Share a database -> must move together as one move group.
MG-04 | .com (public site) | Wave 4 — Critical / high-risk | Most public exposure; applies the proven pattern last.
MG-DX | Splunk / AD / SFTP residuals | Final Cutover / DC-Exit | Prerequisite capability != migrating the platform; move at exit.
For Example: Wave 0 establishes connectivity from AWS to the EXISTING Splunk. Splunk itself stays through the hybrid period and migrates at DC-exit. Needing a capability early does NOT mean migrating that platform early.

## App · SMAP
Application Capture — SMAP
Known target-state (from AWS draft architecture — confirm/correct live)
| Client segment | Wealth Management Clients
| Purpose | SMA product access, account servicing
| Target compute | Amazon ECS Fargate (containerized portal)
| Edge path | Akamai -> Imperva WAF -> Route 53 -> ALB -> ACM
| Data (draft) | Amazon RDS for SQL Server (Multi-AZ) + S3
| Draft wave | Wave 1 — prove the pattern (validate)
Live discovery capture — fill Answer; log any Risk / Dependency / Assumption / Decision as the SME speaks. 'Source' shows Core vs Other Prod-ready.
# | Workshop / Topic | Question | Source | Answer (capture live) | Migration Risk | Dependency | Assumption | Decision needed | Owner
1 | High-Level Application Portfolio Review / Business context | What is the general business purpose of SMAP? | Core | "SMAP runs on ECS Fargate behind the Red Zone edge (Akamai→WAF→R53→ALB). It depends entirely on the AWS Landing Zone — VPC, subnets, IAM, networking — being in place first." | "If LZ/networking/IAM isn't ready, SMAP can't deploy — blocks the Wave-1 pilot." | SMAP → AWS Landing Zone / Radius (= Dep Register D001, Must-move-before → MG-00/Wave 0) | "LZ, Red Zone, IAM/Okta delivered in Wave 0 (MG-00) — AWS draft; confirm." | "Confirm LZ readiness date gates SMAP's Wave-1 start." | "[Parametric app lead / VR platform lead]"
2 | High-Level Application Portfolio Review / Business context | Who are the user personas for SMAP? How do they access the portal? | Core
3 | High-Level Application Portfolio Review / Business context | How often is SMAP used? | Core
4 | High-Level Application Portfolio Review / Architecture walkthrough | Can you walk us through the high-level architecture diagram for SMAP? | Core
5 | High-Level Application Portfolio Review / Architecture walkthrough | How does SMAP interface with shared service domains such as networking, security and access, database, compute, etc.? | Core
6 | High-Level Application Portfolio Review / Domain-specific questions | What are the SLA requirements for this portal? What are the RPO and RTO? | Core
7 | High-Level Application Portfolio Review / Domain-specific questions | What are the high-availability capabilities of the application? | Core
8 | High-Level Application Portfolio Review / Domain-specific questions | What are the DR capabilities of the application? (backup&restore, pilot light, warm standby, active/active) | Core
9 | High-Level Application Portfolio Review / Domain-specific questions | What do you perceive to be the most challenging or complex part(s) of the portal? | Core
10 | High-Level Application Portfolio Review / Application dependencies | What are the key upstream/downstream, on-prem, AWS/Radius, shared-service and external dependencies? What systems are communicated with outside of Azure? | Core
11 | High-Level Application Portfolio Review / SME/Ownership | Which Parametric/MS teams or SMEs own the key application dependencies and integrations? | Core
12 | AWS LZ & Shared Infrastructure Foundation / Discovery Access | What Azure, application, repository, monitoring and documentation access will VR need for discovery? | Core
13 | Application Dispositioning Framework / Disposition Criteria | What criteria determine whether a workload is rehosted, replatformed, re-engineered or handled through another approved pattern? | Core
14 | Application Dispositioning Framework / Constraints | What technical, business, regulatory or platform constraints could influence disposition? | Core
15 | Application Dispositioning Framework / Approval | Who reviews and approves the resulting application disposition? | Core
16 | Application Profile (Prod-ready) | What is the application's business purpose and who are its primary users (internal, partner, public)? | Other Prod-ready
17 | Application Profile (Prod-ready) | What is the business criticality tier (e.g. Tier 1 critical / Tier 2 important / Tier 3 standard) and why? | Other Prod-ready
18 | Application Profile (Prod-ready) | Is this application public-facing / internet-exposed, partner-facing, or internal-only? | Other Prod-ready
19 | Application Profile (Prod-ready) | What business processes break if this app is down for 1 hour? 4 hours? 1 day? | Other Prod-ready
20 | Application Profile (Prod-ready) | Are there seasonal / cyclical peaks (month-end, quarter-end, trading hours) that constrain cutover windows? | Other Prod-ready
21 | Application Profile (Prod-ready) | Is the application subject to regulatory / compliance obligations (SOX, SEC, PCI, data residency)? | Other Prod-ready
22 | Application Profile (Prod-ready) | Who is the technical owner and who signs off go/no-go for this app's cutover? | Other Prod-ready
23 | Application Profile (Prod-ready) | Is the app actively developed, in maintenance, or candidate for retire/replace? | Other Prod-ready
24 | Application Profile (Prod-ready) | Are there any planned business changes (M&A, product sunset) that affect migration timing? | Other Prod-ready
25 | Application Profile (Prod-ready) | What is the acceptable business downtime for cutover and is a maintenance window pre-approved? | Other Prod-ready
26 | Architecture (Prod-ready) | What is the application architecture (monolith, microservices, N-tier, serverless)? | Other Prod-ready
27 | Architecture (Prod-ready) | Which Azure App Service plan(s) host it, and Windows or Linux? | Other Prod-ready
28 | Architecture (Prod-ready) | What language/runtime and framework versions (e.g. .NET Framework vs .NET Core, Node, Java)? | Other Prod-ready
29 | Architecture (Prod-ready) | Is the app already containerized (Docker)? If not, any blockers to containerizing (Win auth, GAC, COM, native deps)? | Other Prod-ready
30 | Architecture (Prod-ready) | How many environments exist (dev/test/stage/prod) and do they differ materially? | Other Prod-ready
31 | Architecture (Prod-ready) | What are current compute sizing / scaling settings (instance count, autoscale rules, CPU/mem)? | Other Prod-ready
32 | Architecture (Prod-ready) | Does the app rely on in-memory session / sticky sessions / local disk state? | Other Prod-ready
33 | Architecture (Prod-ready) | Are there Windows-specific dependencies (IIS modules, Windows auth/Kerberos, MSMQ, scheduled tasks)? | Other Prod-ready
34 | Architecture (Prod-ready) | Any WebJobs / background workers / cron inside the App Service? | Other Prod-ready
35 | Architecture (Prod-ready) | What is the config/secret injection method today (App Settings, Key Vault refs, env vars)? | Other Prod-ready
36 | Integration (Prod-ready) | List every system this app CALLS (synchronous APIs, DB, queue, file) — internal and external. | Other Prod-ready
37 | Integration (Prod-ready) | List every system that CALLS this app (upstream consumers). | Other Prod-ready
38 | Integration (Prod-ready) | Does the app use Azure Service Bus (queues/topics)? Which namespaces and for what flows? | Other Prod-ready
39 | Integration (Prod-ready) | Does the app publish/consume Event Hubs streams? | Other Prod-ready
40 | Integration (Prod-ready) | Does it depend on APIM-fronted APIs? Which, and are they internal or partner? | Other Prod-ready
41 | Integration (Prod-ready) | Are there partner / third-party integrations (Salesforce, SendGrid, payment, market data)? Auth method? | Other Prod-ready
42 | Integration (Prod-ready) | Does the app reach on-prem systems (PCR, Argos, Union, AD, file shares, SFTP)? Over what connectivity? | Other Prod-ready
43 | Integration (Prod-ready) | For each on-prem dependency: must it move BEFORE, WITH, LATER, can it STAY, or is it a DC-exit blocker? | Other Prod-ready
44 | Integration (Prod-ready) | Are there hard-coded IPs, hostnames, or on-prem DNS names in config or code? | Other Prod-ready
45 | Integration (Prod-ready) | What authentication is used between services (mTLS, API keys, OAuth, Windows auth)? | Other Prod-ready
46 | Integration (Prod-ready) | Are there scheduled file transfers (SFTP) in/out? Endpoints and schedules? | Other Prod-ready
47 | Integration (Prod-ready) | Does the app send email (SMTP / SendGrid)? Relay host? | Other Prod-ready
48 | HA & DR (Prod-ready) | What are the current HA settings (zones, instances, load balancing)? | Other Prod-ready
49 | HA & DR (Prod-ready) | What are the formal RTO and RPO targets for this application? | Other Prod-ready
50 | HA & DR (Prod-ready) | Is there a documented DR plan and when was it last tested? | Other Prod-ready
51 | HA & DR (Prod-ready) | Is multi-region required (us-west-2 / us-east-1) or single-region acceptable? | Other Prod-ready
52 | HA & DR (Prod-ready) | What backup/restore tooling is used and what are retention requirements? | Other Prod-ready
53 | Traffic & Load (Prod-ready) | What is the request volume: average and PEAK requests/sec (or per minute) for this app's key endpoints? | Other Prod-ready
54 | Traffic & Load (Prod-ready) | What is the daily/weekly traffic SHAPE (steady, business-hours spike, batch burst, overnight)? | Other Prod-ready
55 | Traffic & Load (Prod-ready) | What is the peak-to-average ratio and how fast does traffic ramp (seconds vs minutes)? | Other Prod-ready
56 | Traffic & Load (Prod-ready) | Are there known/announced events (campaigns, quarter-end, market open) that multiply load? By how much? | Other Prod-ready
57 | Traffic & Load (Prod-ready) | Is there rate limiting / throttling in place today (APIM policies, per-client quotas)? What limits? | Other Prod-ready
58 | Traffic & Load (Prod-ready) | Do any downstream/partner systems impose rate limits we must respect (calls/sec, daily quota)? | Other Prod-ready
59 | Traffic & Load (Prod-ready) | What happens today when limits are exceeded (429s, queueing, drop, retry)? Expected behavior on AWS? | Other Prod-ready
60 | Traffic & Load (Prod-ready) | Are there bursty/async workloads better served by queue+worker than always-on compute? | Other Prod-ready
61 | Traffic & Load (Prod-ready) | What is the request SIZE profile (typical and max payload) and any large-upload/download paths? | Other Prod-ready
62 | Traffic & Load (Prod-ready) | What concurrency does the app sustain (concurrent users / in-flight requests) at peak? | Other Prod-ready
63 | Performance & SLA (Prod-ready) | What are the current latency numbers (p50/p95/p99) for key transactions? | Other Prod-ready
64 | Performance & SLA (Prod-ready) | What latency/response-time SLA or user expectation must be preserved post-migration? | Other Prod-ready
65 | Performance & SLA (Prod-ready) | What availability SLA/SLO applies (e.g. 99.9%)? Is it contractual? | Other Prod-ready
66 | Performance & SLA (Prod-ready) | What is the current CPU/memory utilization profile (avg & peak) per component? | Other Prod-ready
67 | Performance & SLA (Prod-ready) | What are database latency hotspots (slow queries, lock contention, long transactions)? | Other Prod-ready
68 | Performance & SLA (Prod-ready) | Are there components sensitive to cold starts or warm-up (JIT, cache priming, connection pools)? | Other Prod-ready
69 | Performance & SLA (Prod-ready) | Is there a documented performance/load test baseline we can replay on AWS to compare? | Other Prod-ready
70 | Performance & SLA (Prod-ready) | Which transactions are latency-critical vs tolerant (user-facing vs background)? | Other Prod-ready
71 | Performance & SLA (Prod-ready) | What is the latency budget between tiers (web→app→DB→dependency) and any sub-ms sensitivity? | Other Prod-ready
72 | Scalability (Prod-ready) | What is the 1–3 year growth projection (users, transactions, data) for this app? | Other Prod-ready
73 | Scalability (Prod-ready) | What is the current scaling model (vertical, horizontal, manual, auto) and its triggers? | Other Prod-ready
74 | Scalability (Prod-ready) | Is the workload elastic (scales to zero / scales down off-hours) or always-on? | Other Prod-ready
75 | Scalability (Prod-ready) | Are there hard ceilings today (license cores, connection pools, single-threaded components)? | Other Prod-ready
76 | Scalability (Prod-ready) | What are the database scaling limits (max connections, IOPS, storage) hit or near today? | Other Prod-ready
77 | Scalability (Prod-ready) | Is multi-tenancy a factor (per-tenant isolation, noisy-neighbor, per-tenant scaling)? | Other Prod-ready
Derived disposition (two birds, one stone) — filled from the answers above
| Current platform signal | (e.g. Azure App Service / Azure SQL / Service Bus)
| Target AWS service | (e.g. ECS Fargate / RDS SQL Server / SQS-SNS)
| 7R disposition | (Rehost / Replatform / Re-architect / ...)
| Move group | (which apps/data move together)
| Draft wave + rationale | (computed, not hand-ranked)

## App · IPORT
Application Capture — IPORT
Known target-state (from AWS draft architecture — confirm/correct live)
| Client segment | Institutional Clients
| Purpose | Secure document access, reports, invoices
| Target compute | Amazon ECS Fargate (containerized portal)
| Edge path | Akamai -> Imperva WAF -> Route 53 -> ALB -> ACM
| Data (draft) | Amazon RDS for SQL Server (Multi-AZ) + S3
| Draft wave | Wave 2 — shares DB with IMAT (validate)
Live discovery capture — fill Answer; log any Risk / Dependency / Assumption / Decision as the SME speaks. 'Source' shows Core vs Other Prod-ready.
# | Workshop / Topic | Question | Source | Answer (capture live) | Migration Risk | Dependency | Assumption | Decision needed | Owner
1 | High-Level Application Portfolio Review / Business context | What is the general business purpose of IPORT? | Core
2 | High-Level Application Portfolio Review / Business context | Who are the user personas for IPORT? How do they access the portal? | Core
3 | High-Level Application Portfolio Review / Business context | How often is IPORT used? | Core
4 | High-Level Application Portfolio Review / Architecture walkthrough | Can you walk us through the high-level architecture diagram for IPORT? | Core
5 | High-Level Application Portfolio Review / Architecture walkthrough | How does IPORT interface with domains such as networking, security and access, database, compute, etc.? | Core
6 | High-Level Application Portfolio Review / Domain-specific questions | What are the SLA requirements for this portal? What are the RPO and RTO? | Core
7 | High-Level Application Portfolio Review / Domain-specific questions | What are the high-availability capabilities of the application? | Core
8 | High-Level Application Portfolio Review / Domain-specific questions | What are the DR capabilities of the application? (backup&restore, pilot light, warm standby, active/active) | Core
9 | High-Level Application Portfolio Review / Domain-specific questions | What do you perceive to be the most challenging or complex part(s) of the portal? | Core
10 | High-Level Application Portfolio Review / Application dependencies | What are the key upstream/downstream, on-prem, AWS/Radius, shared-service and external dependencies? What systems are communicated with outside of Azure? | Core
11 | High-Level Application Portfolio Review / SME/Ownership | Which Parametric/MS teams or SMEs own the key application dependencies and integrations? | Core
12 | AWS LZ & Shared Infrastructure Foundation / Discovery Access | What Azure, application, repository, monitoring and documentation access will VR need for discovery? | Core
13 | Application Dispositioning Framework / Disposition Criteria | What criteria determine whether a workload is rehosted, replatformed, re-engineered or handled through another approved pattern? | Core
14 | Application Dispositioning Framework / Constraints | What technical, business, regulatory or platform constraints could influence disposition? | Core
15 | Application Dispositioning Framework / Approval | Who reviews and approves the resulting application disposition? | Core
16 | Application Profile (Prod-ready) | What is the application's business purpose and who are its primary users (internal, partner, public)? | Other Prod-ready
17 | Application Profile (Prod-ready) | What is the business criticality tier (e.g. Tier 1 critical / Tier 2 important / Tier 3 standard) and why? | Other Prod-ready
18 | Application Profile (Prod-ready) | Is this application public-facing / internet-exposed, partner-facing, or internal-only? | Other Prod-ready
19 | Application Profile (Prod-ready) | What business processes break if this app is down for 1 hour? 4 hours? 1 day? | Other Prod-ready
20 | Application Profile (Prod-ready) | Are there seasonal / cyclical peaks (month-end, quarter-end, trading hours) that constrain cutover windows? | Other Prod-ready
21 | Application Profile (Prod-ready) | Is the application subject to regulatory / compliance obligations (SOX, SEC, PCI, data residency)? | Other Prod-ready
22 | Application Profile (Prod-ready) | Who is the technical owner and who signs off go/no-go for this app's cutover? | Other Prod-ready
23 | Application Profile (Prod-ready) | Is the app actively developed, in maintenance, or candidate for retire/replace? | Other Prod-ready
24 | Application Profile (Prod-ready) | Are there any planned business changes (M&A, product sunset) that affect migration timing? | Other Prod-ready
25 | Application Profile (Prod-ready) | What is the acceptable business downtime for cutover and is a maintenance window pre-approved? | Other Prod-ready
26 | Architecture (Prod-ready) | What is the application architecture (monolith, microservices, N-tier, serverless)? | Other Prod-ready
27 | Architecture (Prod-ready) | Which Azure App Service plan(s) host it, and Windows or Linux? | Other Prod-ready
28 | Architecture (Prod-ready) | What language/runtime and framework versions (e.g. .NET Framework vs .NET Core, Node, Java)? | Other Prod-ready
29 | Architecture (Prod-ready) | Is the app already containerized (Docker)? If not, any blockers to containerizing (Win auth, GAC, COM, native deps)? | Other Prod-ready
30 | Architecture (Prod-ready) | How many environments exist (dev/test/stage/prod) and do they differ materially? | Other Prod-ready
31 | Architecture (Prod-ready) | What are current compute sizing / scaling settings (instance count, autoscale rules, CPU/mem)? | Other Prod-ready
32 | Architecture (Prod-ready) | Does the app rely on in-memory session / sticky sessions / local disk state? | Other Prod-ready
33 | Architecture (Prod-ready) | Are there Windows-specific dependencies (IIS modules, Windows auth/Kerberos, MSMQ, scheduled tasks)? | Other Prod-ready
34 | Architecture (Prod-ready) | Any WebJobs / background workers / cron inside the App Service? | Other Prod-ready
35 | Architecture (Prod-ready) | What is the config/secret injection method today (App Settings, Key Vault refs, env vars)? | Other Prod-ready
36 | Integration (Prod-ready) | List every system this app CALLS (synchronous APIs, DB, queue, file) — internal and external. | Other Prod-ready
37 | Integration (Prod-ready) | List every system that CALLS this app (upstream consumers). | Other Prod-ready
38 | Integration (Prod-ready) | Does the app use Azure Service Bus (queues/topics)? Which namespaces and for what flows? | Other Prod-ready
39 | Integration (Prod-ready) | Does the app publish/consume Event Hubs streams? | Other Prod-ready
40 | Integration (Prod-ready) | Does it depend on APIM-fronted APIs? Which, and are they internal or partner? | Other Prod-ready
41 | Integration (Prod-ready) | Are there partner / third-party integrations (Salesforce, SendGrid, payment, market data)? Auth method? | Other Prod-ready
42 | Integration (Prod-ready) | Does the app reach on-prem systems (PCR, Argos, Union, AD, file shares, SFTP)? Over what connectivity? | Other Prod-ready
43 | Integration (Prod-ready) | For each on-prem dependency: must it move BEFORE, WITH, LATER, can it STAY, or is it a DC-exit blocker? | Other Prod-ready
44 | Integration (Prod-ready) | Are there hard-coded IPs, hostnames, or on-prem DNS names in config or code? | Other Prod-ready
45 | Integration (Prod-ready) | What authentication is used between services (mTLS, API keys, OAuth, Windows auth)? | Other Prod-ready
46 | Integration (Prod-ready) | Are there scheduled file transfers (SFTP) in/out? Endpoints and schedules? | Other Prod-ready
47 | Integration (Prod-ready) | Does the app send email (SMTP / SendGrid)? Relay host? | Other Prod-ready
48 | HA & DR (Prod-ready) | What are the current HA settings (zones, instances, load balancing)? | Other Prod-ready
49 | HA & DR (Prod-ready) | What are the formal RTO and RPO targets for this application? | Other Prod-ready
50 | HA & DR (Prod-ready) | Is there a documented DR plan and when was it last tested? | Other Prod-ready
51 | HA & DR (Prod-ready) | Is multi-region required (us-west-2 / us-east-1) or single-region acceptable? | Other Prod-ready
52 | HA & DR (Prod-ready) | What backup/restore tooling is used and what are retention requirements? | Other Prod-ready
53 | Traffic & Load (Prod-ready) | What is the request volume: average and PEAK requests/sec (or per minute) for this app's key endpoints? | Other Prod-ready
54 | Traffic & Load (Prod-ready) | What is the daily/weekly traffic SHAPE (steady, business-hours spike, batch burst, overnight)? | Other Prod-ready
55 | Traffic & Load (Prod-ready) | What is the peak-to-average ratio and how fast does traffic ramp (seconds vs minutes)? | Other Prod-ready
56 | Traffic & Load (Prod-ready) | Are there known/announced events (campaigns, quarter-end, market open) that multiply load? By how much? | Other Prod-ready
57 | Traffic & Load (Prod-ready) | Is there rate limiting / throttling in place today (APIM policies, per-client quotas)? What limits? | Other Prod-ready
58 | Traffic & Load (Prod-ready) | Do any downstream/partner systems impose rate limits we must respect (calls/sec, daily quota)? | Other Prod-ready
59 | Traffic & Load (Prod-ready) | What happens today when limits are exceeded (429s, queueing, drop, retry)? Expected behavior on AWS? | Other Prod-ready
60 | Traffic & Load (Prod-ready) | Are there bursty/async workloads better served by queue+worker than always-on compute? | Other Prod-ready
61 | Traffic & Load (Prod-ready) | What is the request SIZE profile (typical and max payload) and any large-upload/download paths? | Other Prod-ready
62 | Traffic & Load (Prod-ready) | What concurrency does the app sustain (concurrent users / in-flight requests) at peak? | Other Prod-ready
63 | Performance & SLA (Prod-ready) | What are the current latency numbers (p50/p95/p99) for key transactions? | Other Prod-ready
64 | Performance & SLA (Prod-ready) | What latency/response-time SLA or user expectation must be preserved post-migration? | Other Prod-ready
65 | Performance & SLA (Prod-ready) | What availability SLA/SLO applies (e.g. 99.9%)? Is it contractual? | Other Prod-ready
66 | Performance & SLA (Prod-ready) | What is the current CPU/memory utilization profile (avg & peak) per component? | Other Prod-ready
67 | Performance & SLA (Prod-ready) | What are database latency hotspots (slow queries, lock contention, long transactions)? | Other Prod-ready
68 | Performance & SLA (Prod-ready) | Are there components sensitive to cold starts or warm-up (JIT, cache priming, connection pools)? | Other Prod-ready
69 | Performance & SLA (Prod-ready) | Is there a documented performance/load test baseline we can replay on AWS to compare? | Other Prod-ready
70 | Performance & SLA (Prod-ready) | Which transactions are latency-critical vs tolerant (user-facing vs background)? | Other Prod-ready
71 | Performance & SLA (Prod-ready) | What is the latency budget between tiers (web→app→DB→dependency) and any sub-ms sensitivity? | Other Prod-ready
72 | Scalability (Prod-ready) | What is the 1–3 year growth projection (users, transactions, data) for this app? | Other Prod-ready
73 | Scalability (Prod-ready) | What is the current scaling model (vertical, horizontal, manual, auto) and its triggers? | Other Prod-ready
74 | Scalability (Prod-ready) | Is the workload elastic (scales to zero / scales down off-hours) or always-on? | Other Prod-ready
75 | Scalability (Prod-ready) | Are there hard ceilings today (license cores, connection pools, single-threaded components)? | Other Prod-ready
76 | Scalability (Prod-ready) | What are the database scaling limits (max connections, IOPS, storage) hit or near today? | Other Prod-ready
77 | Scalability (Prod-ready) | Is multi-tenancy a factor (per-tenant isolation, noisy-neighbor, per-tenant scaling)? | Other Prod-ready
Derived disposition (two birds, one stone) — filled from the answers above
| Current platform signal | (e.g. Azure App Service / Azure SQL / Service Bus)
| Target AWS service | (e.g. ECS Fargate / RDS SQL Server / SQS-SNS)
| 7R disposition | (Rehost / Replatform / Re-architect / ...)
| Move group | (which apps/data move together)
| Draft wave + rationale | (computed, not hand-ranked)

## App · IMAT
Application Capture — IMAT
Known target-state (from AWS draft architecture — confirm/correct live)
| Client segment | Financial Advisors
| Purpose | Model & benchmark management
| Target compute | Amazon ECS Fargate; refactor candidacy flagged
| Edge path | Akamai -> Imperva WAF -> Route 53 -> ALB -> ACM
| Data (draft) | Amazon RDS for SQL Server (Multi-AZ) + S3
| Draft wave | Wave 2 — shares DB with IPORT (validate)
Live discovery capture — fill Answer; log any Risk / Dependency / Assumption / Decision as the SME speaks. 'Source' shows Core vs Other Prod-ready.
# | Workshop / Topic | Question | Source | Answer (capture live) | Migration Risk | Dependency | Assumption | Decision needed | Owner
1 | High-Level Application Portfolio Review / Business context | What is the general business purpose of IMAT? | Core
2 | High-Level Application Portfolio Review / Business context | Who are the user personas for IMAT? How do they access the portal? | Core
3 | High-Level Application Portfolio Review / Business context | How often is IMAT used? | Core
4 | High-Level Application Portfolio Review / Architecture walkthrough | Can you walk us through the high-level architecture diagram for IMAT? | Core
5 | High-Level Application Portfolio Review / Refactor candidacy | What specific design components / attributes of IMAT make it a candidate to be refactored? | Core
6 | High-Level Application Portfolio Review / Architecture walkthrough | How does IMAT interface with domains such as networking, security and access, database, compute, etc.? | Core
7 | High-Level Application Portfolio Review / Domain-specific questions | What are the SLA requirements for this portal? What are the RPO and RTO? | Core
8 | High-Level Application Portfolio Review / Domain-specific questions | What are the high-availability capabilities of the application? | Core
9 | High-Level Application Portfolio Review / Domain-specific questions | What are the DR capabilities of the application? (backup&restore, pilot light, warm standby, active/active) | Core
10 | High-Level Application Portfolio Review / Domain-specific questions | What do you perceive to be the most challenging or complex part(s) of the portal? | Core
11 | High-Level Application Portfolio Review / Application dependencies | What are the key upstream/downstream, on-prem, AWS/Radius, shared-service and external dependencies? What systems are communicated with outside of Azure? | Core
12 | High-Level Application Portfolio Review / SME/Ownership | Which Parametric/MS teams or SMEs own the key application dependencies and integrations? | Core
13 | AWS LZ & Shared Infrastructure Foundation / Discovery Access | What Azure, application, repository, monitoring and documentation access will VR need for discovery? | Core
14 | Application Dispositioning Framework / Disposition Criteria | What criteria determine whether a workload is rehosted, replatformed, re-engineered or handled through another approved pattern? | Core
15 | Application Dispositioning Framework / Constraints | What technical, business, regulatory or platform constraints could influence disposition? | Core
16 | Application Dispositioning Framework / Approval | Who reviews and approves the resulting application disposition? | Core
17 | Application Profile (Prod-ready) | What is the application's business purpose and who are its primary users (internal, partner, public)? | Other Prod-ready
18 | Application Profile (Prod-ready) | What is the business criticality tier (e.g. Tier 1 critical / Tier 2 important / Tier 3 standard) and why? | Other Prod-ready
19 | Application Profile (Prod-ready) | Is this application public-facing / internet-exposed, partner-facing, or internal-only? | Other Prod-ready
20 | Application Profile (Prod-ready) | What business processes break if this app is down for 1 hour? 4 hours? 1 day? | Other Prod-ready
21 | Application Profile (Prod-ready) | Are there seasonal / cyclical peaks (month-end, quarter-end, trading hours) that constrain cutover windows? | Other Prod-ready
22 | Application Profile (Prod-ready) | Is the application subject to regulatory / compliance obligations (SOX, SEC, PCI, data residency)? | Other Prod-ready
23 | Application Profile (Prod-ready) | Who is the technical owner and who signs off go/no-go for this app's cutover? | Other Prod-ready
24 | Application Profile (Prod-ready) | Is the app actively developed, in maintenance, or candidate for retire/replace? | Other Prod-ready
25 | Application Profile (Prod-ready) | Are there any planned business changes (M&A, product sunset) that affect migration timing? | Other Prod-ready
26 | Application Profile (Prod-ready) | What is the acceptable business downtime for cutover and is a maintenance window pre-approved? | Other Prod-ready
27 | Architecture (Prod-ready) | What is the application architecture (monolith, microservices, N-tier, serverless)? | Other Prod-ready
28 | Architecture (Prod-ready) | Which Azure App Service plan(s) host it, and Windows or Linux? | Other Prod-ready
29 | Architecture (Prod-ready) | What language/runtime and framework versions (e.g. .NET Framework vs .NET Core, Node, Java)? | Other Prod-ready
30 | Architecture (Prod-ready) | Is the app already containerized (Docker)? If not, any blockers to containerizing (Win auth, GAC, COM, native deps)? | Other Prod-ready
31 | Architecture (Prod-ready) | How many environments exist (dev/test/stage/prod) and do they differ materially? | Other Prod-ready
32 | Architecture (Prod-ready) | What are current compute sizing / scaling settings (instance count, autoscale rules, CPU/mem)? | Other Prod-ready
33 | Architecture (Prod-ready) | Does the app rely on in-memory session / sticky sessions / local disk state? | Other Prod-ready
34 | Architecture (Prod-ready) | Are there Windows-specific dependencies (IIS modules, Windows auth/Kerberos, MSMQ, scheduled tasks)? | Other Prod-ready
35 | Architecture (Prod-ready) | Any WebJobs / background workers / cron inside the App Service? | Other Prod-ready
36 | Architecture (Prod-ready) | What is the config/secret injection method today (App Settings, Key Vault refs, env vars)? | Other Prod-ready
37 | Integration (Prod-ready) | List every system this app CALLS (synchronous APIs, DB, queue, file) — internal and external. | Other Prod-ready
38 | Integration (Prod-ready) | List every system that CALLS this app (upstream consumers). | Other Prod-ready
39 | Integration (Prod-ready) | Does the app use Azure Service Bus (queues/topics)? Which namespaces and for what flows? | Other Prod-ready
40 | Integration (Prod-ready) | Does the app publish/consume Event Hubs streams? | Other Prod-ready
41 | Integration (Prod-ready) | Does it depend on APIM-fronted APIs? Which, and are they internal or partner? | Other Prod-ready
42 | Integration (Prod-ready) | Are there partner / third-party integrations (Salesforce, SendGrid, payment, market data)? Auth method? | Other Prod-ready
43 | Integration (Prod-ready) | Does the app reach on-prem systems (PCR, Argos, Union, AD, file shares, SFTP)? Over what connectivity? | Other Prod-ready
44 | Integration (Prod-ready) | For each on-prem dependency: must it move BEFORE, WITH, LATER, can it STAY, or is it a DC-exit blocker? | Other Prod-ready
45 | Integration (Prod-ready) | Are there hard-coded IPs, hostnames, or on-prem DNS names in config or code? | Other Prod-ready
46 | Integration (Prod-ready) | What authentication is used between services (mTLS, API keys, OAuth, Windows auth)? | Other Prod-ready
47 | Integration (Prod-ready) | Are there scheduled file transfers (SFTP) in/out? Endpoints and schedules? | Other Prod-ready
48 | Integration (Prod-ready) | Does the app send email (SMTP / SendGrid)? Relay host? | Other Prod-ready
49 | HA & DR (Prod-ready) | What are the current HA settings (zones, instances, load balancing)? | Other Prod-ready
50 | HA & DR (Prod-ready) | What are the formal RTO and RPO targets for this application? | Other Prod-ready
51 | HA & DR (Prod-ready) | Is there a documented DR plan and when was it last tested? | Other Prod-ready
52 | HA & DR (Prod-ready) | Is multi-region required (us-west-2 / us-east-1) or single-region acceptable? | Other Prod-ready
53 | HA & DR (Prod-ready) | What backup/restore tooling is used and what are retention requirements? | Other Prod-ready
54 | Traffic & Load (Prod-ready) | What is the request volume: average and PEAK requests/sec (or per minute) for this app's key endpoints? | Other Prod-ready
55 | Traffic & Load (Prod-ready) | What is the daily/weekly traffic SHAPE (steady, business-hours spike, batch burst, overnight)? | Other Prod-ready
56 | Traffic & Load (Prod-ready) | What is the peak-to-average ratio and how fast does traffic ramp (seconds vs minutes)? | Other Prod-ready
57 | Traffic & Load (Prod-ready) | Are there known/announced events (campaigns, quarter-end, market open) that multiply load? By how much? | Other Prod-ready
58 | Traffic & Load (Prod-ready) | Is there rate limiting / throttling in place today (APIM policies, per-client quotas)? What limits? | Other Prod-ready
59 | Traffic & Load (Prod-ready) | Do any downstream/partner systems impose rate limits we must respect (calls/sec, daily quota)? | Other Prod-ready
60 | Traffic & Load (Prod-ready) | What happens today when limits are exceeded (429s, queueing, drop, retry)? Expected behavior on AWS? | Other Prod-ready
61 | Traffic & Load (Prod-ready) | Are there bursty/async workloads better served by queue+worker than always-on compute? | Other Prod-ready
62 | Traffic & Load (Prod-ready) | What is the request SIZE profile (typical and max payload) and any large-upload/download paths? | Other Prod-ready
63 | Traffic & Load (Prod-ready) | What concurrency does the app sustain (concurrent users / in-flight requests) at peak? | Other Prod-ready
64 | Performance & SLA (Prod-ready) | What are the current latency numbers (p50/p95/p99) for key transactions? | Other Prod-ready
65 | Performance & SLA (Prod-ready) | What latency/response-time SLA or user expectation must be preserved post-migration? | Other Prod-ready
66 | Performance & SLA (Prod-ready) | What availability SLA/SLO applies (e.g. 99.9%)? Is it contractual? | Other Prod-ready
67 | Performance & SLA (Prod-ready) | What is the current CPU/memory utilization profile (avg & peak) per component? | Other Prod-ready
68 | Performance & SLA (Prod-ready) | What are database latency hotspots (slow queries, lock contention, long transactions)? | Other Prod-ready
69 | Performance & SLA (Prod-ready) | Are there components sensitive to cold starts or warm-up (JIT, cache priming, connection pools)? | Other Prod-ready
70 | Performance & SLA (Prod-ready) | Is there a documented performance/load test baseline we can replay on AWS to compare? | Other Prod-ready
71 | Performance & SLA (Prod-ready) | Which transactions are latency-critical vs tolerant (user-facing vs background)? | Other Prod-ready
72 | Performance & SLA (Prod-ready) | What is the latency budget between tiers (web→app→DB→dependency) and any sub-ms sensitivity? | Other Prod-ready
73 | Scalability (Prod-ready) | What is the 1–3 year growth projection (users, transactions, data) for this app? | Other Prod-ready
74 | Scalability (Prod-ready) | What is the current scaling model (vertical, horizontal, manual, auto) and its triggers? | Other Prod-ready
75 | Scalability (Prod-ready) | Is the workload elastic (scales to zero / scales down off-hours) or always-on? | Other Prod-ready
76 | Scalability (Prod-ready) | Are there hard ceilings today (license cores, connection pools, single-threaded components)? | Other Prod-ready
77 | Scalability (Prod-ready) | What are the database scaling limits (max connections, IOPS, storage) hit or near today? | Other Prod-ready
78 | Scalability (Prod-ready) | Is multi-tenancy a factor (per-tenant isolation, noisy-neighbor, per-tenant scaling)? | Other Prod-ready
Derived disposition (two birds, one stone) — filled from the answers above
| Current platform signal | (e.g. Azure App Service / Azure SQL / Service Bus)
| Target AWS service | (e.g. ECS Fargate / RDS SQL Server / SQS-SNS)
| 7R disposition | (Rehost / Replatform / Re-architect / ...)
| Move group | (which apps/data move together)
| Draft wave + rationale | (computed, not hand-ranked)

## App · .com
Application Capture — .com
Known target-state (from AWS draft architecture — confirm/correct live)
| Client segment | Public Users
| Purpose | Services, investment strategies, research
| Target compute | Amazon ECS Fargate (public web)
| Edge path | Akamai -> Imperva WAF -> Public DNS/Route 53 -> ALB -> ACM
| Data (draft) | Amazon S3 (static/content) + RDS as needed
| Draft wave | Wave 4 — most public exposure (validate)
Live discovery capture — fill Answer; log any Risk / Dependency / Assumption / Decision as the SME speaks. 'Source' shows Core vs Other Prod-ready.
# | Workshop / Topic | Question | Source | Answer (capture live) | Migration Risk | Dependency | Assumption | Decision needed | Owner
1 | High-Level Application Portfolio Review / Business context | What is the general business purpose of .com? | Core
2 | High-Level Application Portfolio Review / Business context | Who are the user personas for .com? How do they access the portal? | Core
3 | High-Level Application Portfolio Review / Business context | How often is .com used? | Core
4 | High-Level Application Portfolio Review / Architecture walkthrough | Can you walk us through the high-level architecture diagram for .com? | Core
5 | High-Level Application Portfolio Review / Architecture walkthrough | How does .com interface with domains such as networking, security and access, database, compute, etc.? | Core
6 | High-Level Application Portfolio Review / Domain-specific questions | What are the SLA requirements for this portal? What are the RPO and RTO? | Core
7 | High-Level Application Portfolio Review / Domain-specific questions | What are the high-availability capabilities of the application? | Core
8 | High-Level Application Portfolio Review / Domain-specific questions | What are the DR capabilities of the application? (backup&restore, pilot light, warm standby, active/active) | Core
9 | High-Level Application Portfolio Review / Domain-specific questions | What do you perceive to be the most challenging or complex part(s) of the portal? | Core
10 | High-Level Application Portfolio Review / Application dependencies | What are the key upstream/downstream, on-prem, AWS/Radius, shared-service and external dependencies? What systems are communicated with outside of Azure? | Core
11 | High-Level Application Portfolio Review / SME/Ownership | Which Parametric/MS teams or SMEs own the key application dependencies and integrations? | Core
12 | AWS LZ & Shared Infrastructure Foundation / Discovery Access | What Azure, application, repository, monitoring and documentation access will VR need for discovery? | Core
13 | Application Dispositioning Framework / Disposition Criteria | What criteria determine whether a workload is rehosted, replatformed, re-engineered or handled through another approved pattern? | Core
14 | Application Dispositioning Framework / Constraints | What technical, business, regulatory or platform constraints could influence disposition? | Core
15 | Application Dispositioning Framework / Approval | Who reviews and approves the resulting application disposition? | Core
16 | Application Profile (Prod-ready) | What is the application's business purpose and who are its primary users (internal, partner, public)? | Other Prod-ready
17 | Application Profile (Prod-ready) | What is the business criticality tier (e.g. Tier 1 critical / Tier 2 important / Tier 3 standard) and why? | Other Prod-ready
18 | Application Profile (Prod-ready) | Is this application public-facing / internet-exposed, partner-facing, or internal-only? | Other Prod-ready
19 | Application Profile (Prod-ready) | What business processes break if this app is down for 1 hour? 4 hours? 1 day? | Other Prod-ready
20 | Application Profile (Prod-ready) | Are there seasonal / cyclical peaks (month-end, quarter-end, trading hours) that constrain cutover windows? | Other Prod-ready
21 | Application Profile (Prod-ready) | Is the application subject to regulatory / compliance obligations (SOX, SEC, PCI, data residency)? | Other Prod-ready
22 | Application Profile (Prod-ready) | Who is the technical owner and who signs off go/no-go for this app's cutover? | Other Prod-ready
23 | Application Profile (Prod-ready) | Is the app actively developed, in maintenance, or candidate for retire/replace? | Other Prod-ready
24 | Application Profile (Prod-ready) | Are there any planned business changes (M&A, product sunset) that affect migration timing? | Other Prod-ready
25 | Application Profile (Prod-ready) | What is the acceptable business downtime for cutover and is a maintenance window pre-approved? | Other Prod-ready
26 | Architecture (Prod-ready) | What is the application architecture (monolith, microservices, N-tier, serverless)? | Other Prod-ready
27 | Architecture (Prod-ready) | Which Azure App Service plan(s) host it, and Windows or Linux? | Other Prod-ready
28 | Architecture (Prod-ready) | What language/runtime and framework versions (e.g. .NET Framework vs .NET Core, Node, Java)? | Other Prod-ready
29 | Architecture (Prod-ready) | Is the app already containerized (Docker)? If not, any blockers to containerizing (Win auth, GAC, COM, native deps)? | Other Prod-ready
30 | Architecture (Prod-ready) | How many environments exist (dev/test/stage/prod) and do they differ materially? | Other Prod-ready
31 | Architecture (Prod-ready) | What are current compute sizing / scaling settings (instance count, autoscale rules, CPU/mem)? | Other Prod-ready
32 | Architecture (Prod-ready) | Does the app rely on in-memory session / sticky sessions / local disk state? | Other Prod-ready
33 | Architecture (Prod-ready) | Are there Windows-specific dependencies (IIS modules, Windows auth/Kerberos, MSMQ, scheduled tasks)? | Other Prod-ready
34 | Architecture (Prod-ready) | Any WebJobs / background workers / cron inside the App Service? | Other Prod-ready
35 | Architecture (Prod-ready) | What is the config/secret injection method today (App Settings, Key Vault refs, env vars)? | Other Prod-ready
36 | Integration (Prod-ready) | List every system this app CALLS (synchronous APIs, DB, queue, file) — internal and external. | Other Prod-ready
37 | Integration (Prod-ready) | List every system that CALLS this app (upstream consumers). | Other Prod-ready
38 | Integration (Prod-ready) | Does the app use Azure Service Bus (queues/topics)? Which namespaces and for what flows? | Other Prod-ready
39 | Integration (Prod-ready) | Does the app publish/consume Event Hubs streams? | Other Prod-ready
40 | Integration (Prod-ready) | Does it depend on APIM-fronted APIs? Which, and are they internal or partner? | Other Prod-ready
41 | Integration (Prod-ready) | Are there partner / third-party integrations (Salesforce, SendGrid, payment, market data)? Auth method? | Other Prod-ready
42 | Integration (Prod-ready) | Does the app reach on-prem systems (PCR, Argos, Union, AD, file shares, SFTP)? Over what connectivity? | Other Prod-ready
43 | Integration (Prod-ready) | For each on-prem dependency: must it move BEFORE, WITH, LATER, can it STAY, or is it a DC-exit blocker? | Other Prod-ready
44 | Integration (Prod-ready) | Are there hard-coded IPs, hostnames, or on-prem DNS names in config or code? | Other Prod-ready
45 | Integration (Prod-ready) | What authentication is used between services (mTLS, API keys, OAuth, Windows auth)? | Other Prod-ready
46 | Integration (Prod-ready) | Are there scheduled file transfers (SFTP) in/out? Endpoints and schedules? | Other Prod-ready
47 | Integration (Prod-ready) | Does the app send email (SMTP / SendGrid)? Relay host? | Other Prod-ready
48 | HA & DR (Prod-ready) | What are the current HA settings (zones, instances, load balancing)? | Other Prod-ready
49 | HA & DR (Prod-ready) | What are the formal RTO and RPO targets for this application? | Other Prod-ready
50 | HA & DR (Prod-ready) | Is there a documented DR plan and when was it last tested? | Other Prod-ready
51 | HA & DR (Prod-ready) | Is multi-region required (us-west-2 / us-east-1) or single-region acceptable? | Other Prod-ready
52 | HA & DR (Prod-ready) | What backup/restore tooling is used and what are retention requirements? | Other Prod-ready
53 | Traffic & Load (Prod-ready) | What is the request volume: average and PEAK requests/sec (or per minute) for this app's key endpoints? | Other Prod-ready
54 | Traffic & Load (Prod-ready) | What is the daily/weekly traffic SHAPE (steady, business-hours spike, batch burst, overnight)? | Other Prod-ready
55 | Traffic & Load (Prod-ready) | What is the peak-to-average ratio and how fast does traffic ramp (seconds vs minutes)? | Other Prod-ready
56 | Traffic & Load (Prod-ready) | Are there known/announced events (campaigns, quarter-end, market open) that multiply load? By how much? | Other Prod-ready
57 | Traffic & Load (Prod-ready) | Is there rate limiting / throttling in place today (APIM policies, per-client quotas)? What limits? | Other Prod-ready
58 | Traffic & Load (Prod-ready) | Do any downstream/partner systems impose rate limits we must respect (calls/sec, daily quota)? | Other Prod-ready
59 | Traffic & Load (Prod-ready) | What happens today when limits are exceeded (429s, queueing, drop, retry)? Expected behavior on AWS? | Other Prod-ready
60 | Traffic & Load (Prod-ready) | Are there bursty/async workloads better served by queue+worker than always-on compute? | Other Prod-ready
61 | Traffic & Load (Prod-ready) | What is the request SIZE profile (typical and max payload) and any large-upload/download paths? | Other Prod-ready
62 | Traffic & Load (Prod-ready) | What concurrency does the app sustain (concurrent users / in-flight requests) at peak? | Other Prod-ready
63 | Performance & SLA (Prod-ready) | What are the current latency numbers (p50/p95/p99) for key transactions? | Other Prod-ready
64 | Performance & SLA (Prod-ready) | What latency/response-time SLA or user expectation must be preserved post-migration? | Other Prod-ready
65 | Performance & SLA (Prod-ready) | What availability SLA/SLO applies (e.g. 99.9%)? Is it contractual? | Other Prod-ready
66 | Performance & SLA (Prod-ready) | What is the current CPU/memory utilization profile (avg & peak) per component? | Other Prod-ready
67 | Performance & SLA (Prod-ready) | What are database latency hotspots (slow queries, lock contention, long transactions)? | Other Prod-ready
68 | Performance & SLA (Prod-ready) | Are there components sensitive to cold starts or warm-up (JIT, cache priming, connection pools)? | Other Prod-ready
69 | Performance & SLA (Prod-ready) | Is there a documented performance/load test baseline we can replay on AWS to compare? | Other Prod-ready
70 | Performance & SLA (Prod-ready) | Which transactions are latency-critical vs tolerant (user-facing vs background)? | Other Prod-ready
71 | Performance & SLA (Prod-ready) | What is the latency budget between tiers (web→app→DB→dependency) and any sub-ms sensitivity? | Other Prod-ready
72 | Scalability (Prod-ready) | What is the 1–3 year growth projection (users, transactions, data) for this app? | Other Prod-ready
73 | Scalability (Prod-ready) | What is the current scaling model (vertical, horizontal, manual, auto) and its triggers? | Other Prod-ready
74 | Scalability (Prod-ready) | Is the workload elastic (scales to zero / scales down off-hours) or always-on? | Other Prod-ready
75 | Scalability (Prod-ready) | Are there hard ceilings today (license cores, connection pools, single-threaded components)? | Other Prod-ready
76 | Scalability (Prod-ready) | What are the database scaling limits (max connections, IOPS, storage) hit or near today? | Other Prod-ready
77 | Scalability (Prod-ready) | Is multi-tenancy a factor (per-tenant isolation, noisy-neighbor, per-tenant scaling)? | Other Prod-ready
Derived disposition (two birds, one stone) — filled from the answers above
| Current platform signal | (e.g. Azure App Service / Azure SQL / Service Bus)
| Target AWS service | (e.g. ECS Fargate / RDS SQL Server / SQS-SNS)
| 7R disposition | (Rehost / Replatform / Re-architect / ...)
| Move group | (which apps/data move together)
| Draft wave + rationale | (computed, not hand-ranked)

## RACI
RACI Overview
# | Topic | Question | Answer (capture live) | Ownership/Governance Risk | Dependency | Decision needed | Owner
1 | Decision ownership | Who is accountable for application disposition, target architecture and migration sequencing decisions?
2 | Domain ownership | Who owns application, network, security/IAM, data/DB, platform/LZ, observability and CI/CD decisions/inputs?
3 | Approvals | Who approves SecArch, architecture, production readiness, CAB/change and business go/no-go?
4 | Escalation | What is the escalation path when a dependency, shared service or approval threatens the roadmap?
5 | Delivery ownership | During migration/cutover/hypercare, what is owned by Parametric/MS, AWS and VR, and where does ownership transition?
5 questions (RACI Overview).

## Platform · LZ-Radius
AWS LZ & Shared Infrastructure Foundation
# | Topic | Question | Source | Answer (capture live) | Risk | Dependency | Decision needed | Owner
1 | LZ & Foundation capabilities | What high-level capabilities are handled/owned as part of the LZ & Foundation? (account vending, SCPs, ingress/egress, IAM, etc) | Core
2 | LZ & Foundation capabilities | What is the release schedule for the LZ & Foundation capabilities? | Core
3 | LZ & Foundation capabilities | How do teams request changes to the LZ & Foundation? | Core
4 | LZ & Foundation capabilities | What approvals are required for changes to the LZ & Foundation? | Core
5 | Operational management | What are the specifics of account vending? How long to get them vended and what does the vended environment come with? | Core
6 | Operational management | As Cloud Infrastructure Migration Engineers, what will our access pattern be to AWS accounts? Console and CLI access? | Core
7 | Domain-specific questions | How do digital applications interact with the ingress/egress solution? How do they reach the internet and non-Azure areas of the internal network? | Core
8 | Domain-specific questions | What is the process for raising FW requests, how long does it take, and does it usually work first time? | Core
9 | Domain-specific questions | What observability tools are currently used by Parametric? Native Azure, third-party, or a mix? | Core
10 | Domain-specific questions | What is the logging landscape at Morgan Stanley? Native AWS, third-party, or a mix? | Core
11 | Discovery Access | What Azure, application, repository, monitoring and documentation access will VR need for discovery? | Core
12 | Platform | How do Red Zone, Radius and other shared AWS capabilities relate to the Digital workloads, and which will Digital consume? | Core
13 | ETS / connectivity | What ETS/network capabilities and dependencies are required to connect Digital workloads, on-prem, AWS/shared services and external systems? | Core
14 | IAC | Which Terraform scripts or infrastructure patterns are expected for the Digital workloads? | Core
15 | AWS Access | What AWS account/LZ/Radius access does VR need to validate the environment and migration readiness? | Core
16 | Platform Readiness | Which LZ/Foundation capabilities are available today, which are planned, and which have dependencies/timelines affecting sequencing? | Core
17 | Network | What VNet/subnets and NSGs does the app live in today? Any private endpoints? | Other Prod-ready
18 | Network | What inbound/outbound ports and protocols does the app require? | Other Prod-ready
19 | Network | Is there a dependency on ExpressRoute / site-to-site VPN to on-prem? | Other Prod-ready
20 | Network | What are the latency sensitivities between app and its DB / dependencies? | Other Prod-ready
21 | Network | What DNS zones/records does the app rely on (public + private)? TTLs? | Other Prod-ready
22 | Network | Any fixed egress IP requirements (partner allow-lists, firewall rules)? | Other Prod-ready
23 | Network | Is traffic fronted by Akamai / WAF today? What rules? | Other Prod-ready
24 | Network | Bandwidth required for data migration (DB + blob) and is Direct Connect capacity sufficient? | Other Prod-ready
25 | Security & IAM | How do users authenticate (Okta SSO, Azure AD, local)? Any Azure AD app registrations? | Other Prod-ready
26 | Security & IAM | How do services authenticate to Azure resources (Managed Identity, service principals, conn strings)? | Other Prod-ready
27 | Security & IAM | What secrets/certs live in Key Vault and how are they referenced? | Other Prod-ready
28 | Security & IAM | What RBAC roles / groups govern access and where are they defined? | Other Prod-ready
29 | Security & IAM | Any data classification (PII, PCI, confidential) and encryption requirements (at rest/in transit)? | Other Prod-ready
30 | Security & IAM | Does the app have a Morgan Stanley SecArch approval dependency or control baseline to meet? | Other Prod-ready
31 | Security & IAM | Are there security scanners / endpoint agents that must be present (Qualys, CrowdStrike, etc.)? | Other Prod-ready
32 | Security & IAM | What audit/logging obligations apply (who accessed what, retention period)? | Other Prod-ready
33 | Observability | Where do logs go today (Log Analytics workspace, App Insights, Splunk, DataDog)? | Other Prod-ready
34 | Observability | If logs go to Splunk/DataDog on-prem or SaaS — can AWS ship to the EXISTING platform over connectivity? | Other Prod-ready
35 | Observability | What metrics/alarms exist and who is paged? What are the SLOs? | Other Prod-ready
36 | Observability | Is there distributed tracing today? Instrumented how? | Other Prod-ready
37 | Observability | What dashboards must exist on day 1 after cutover? | Other Prod-ready
38 | Hybrid Operations | During the hybrid period, who owns incident response for this app (Parametric, VR, shared)? | Other Prod-ready
39 | Hybrid Operations | Will monitoring be split (Azure + AWS) during migration, and how are alerts correlated? | Other Prod-ready
40 | Hybrid Operations | What is the expected lifetime of hybrid connectivity (DX/VPN) and its cost owner? | Other Prod-ready
41 | Hybrid Operations | During hybrid, how is identity kept consistent across Azure AD / on-prem AD / Okta / AWS IAM? | Other Prod-ready
42 | Hybrid Operations | Is there a 'no new feature on old platform' freeze policy once migration starts? | Other Prod-ready
43 | Load Balancing | How is traffic load-balanced today (Azure LB, App Gateway, Front Door, Traffic Manager)? L4 or L7? | Other Prod-ready
44 | Load Balancing | Are sticky sessions / session affinity required? By what key (cookie, IP)? | Other Prod-ready
45 | Load Balancing | What health-check endpoints/criteria determine a healthy instance today? | Other Prod-ready
46 | Load Balancing | Is TLS terminated at the LB, passed through, or re-encrypted to backend (mTLS)? | Other Prod-ready
47 | Load Balancing | Are there long-lived connections (WebSockets, SSE, gRPC, keep-alive) or long requests? | Other Prod-ready
48 | Load Balancing | What connection-draining / graceful-shutdown behavior is needed on deploy or scale-in? | Other Prod-ready
49 | Load Balancing | Is global traffic routing / geo-based routing / failover routing used today? | Other Prod-ready
50 | Load Balancing | What is the max/typical number of backend instances behind the LB at peak? | Other Prod-ready
51 | Network Detail | Are there static/whitelisted source IPs that partners or firewalls depend on (ingress or egress)? | Other Prod-ready
52 | Network Detail | Is there any asymmetric routing, NAT, proxy, or hairpin traffic pattern today? | Other Prod-ready
53 | Network Detail | Are there private endpoints / service endpoints to Azure PaaS that need AWS PrivateLink equivalents? | Other Prod-ready
54 | Network Detail | What is the east-west (service-to-service) traffic volume and does it cross AZ/region today? | Other Prod-ready
55 | Network Detail | Are there MTU, jumbo-frame, or packet-size sensitivities (VPN, legacy protocols)? | Other Prod-ready
56 | Network Detail | Any multicast, broadcast, or non-TCP/UDP protocols in use (legacy, clustering)? | Other Prod-ready
57 | Network Detail | What outbound internet dependencies exist (package repos, APIs, telemetry) and their volume? | Other Prod-ready
58 | Network Detail | Are there known network pain points today (latency spikes, saturation, DNS flakiness, retries)? | Other Prod-ready
59 | Network Detail | What DNS resolution patterns exist (split-horizon, conditional forwarders to on-prem)? | Other Prod-ready
60 | MS ETS / Hosting (Context) | Does Morgan Stanley ETS (Enhanced Technology Support) — or any VMware SDDC it operates — host or sit in the data path of the 4 apps? If not, confirm it's out of scope for this Azure->AWS migration. | Other Prod-ready
60 questions (AWS LZ & Shared Infrastructure Foundation).

## Service Onboarding
Service Onboarding Framework
# | Topic | Question | Source | Answer (capture live) | Process/Lead Time Risk | Dependency | Decision needed | Owner
1 | AWS service onboarding | For a given AWS service, what is the submission/request process? | Core
2 | AWS service onboarding | For a given AWS service, how many rounds of review occur? | Core
3 | AWS service onboarding | For a given AWS service, what is the typical duration between request and fulfillment? | Core
4 | AWS service onboarding | For a given AWS service, are there standard security and compliance considerations that apply to all services? | Core
5 | AWS service onboarding | For a given AWS service, what approvals are required? | Core
6 | AWS service onboarding | For a given AWS service, how does the handoff work once it is approved? | Core
7 | Workload onboarding | How do workloads onboard to AWS? | Core
8 | Recent onboarding example | Which recently onboarded service can we use as an example to walk through? | Core
9 | Recent onboarding example | What documentation did that service provide during onboarding? | Core
10 | Recent onboarding example | How long did the onboarding process take for that service? | Core
11 | Recent onboarding example | Which onboarding activities are automated and which require manual requests or approvals? | Core
12 | Lead Time | Which onboarding activities commonly cause delay or require lead time? | Core
13 | DevOps & CI/CD | How is the app built and deployed today (Azure DevOps, GitHub Actions, Jenkins)? Pipeline location? | Other Prod-ready
14 | DevOps & CI/CD | Where is source code hosted and who has access? | Other Prod-ready
15 | DevOps & CI/CD | Is infrastructure defined as code today? If so, in what (ARM/Bicep/Terraform)? | Other Prod-ready
16 | DevOps & CI/CD | What artifact registries are used (ACR, npm, NuGet)? Migrate to ECR? | Other Prod-ready
17 | DevOps & CI/CD | What is the release cadence and is a code freeze feasible during cutover? | Other Prod-ready
18 | DevOps & CI/CD | Does the app have automated tests (unit/integration/smoke) usable for migration validation? | Other Prod-ready
18 questions (Service Onboarding Framework).

## App Dispositioning
Application Dispositioning Framework
# | Topic | Question | Source | Answer (capture live) | Dispositon/Decision Risk | Dependency | Decision needed | Owner
1 | Disposition Criteria | What criteria determine whether a workload is rehosted, replatformed, re-engineered or handled through another approved pattern? | Core | "Criteria: current compute/runtime fit (containerizable → ECS Fargate), data compatibility (SQL → RDS via DMS), code changes required (Windows/.NET deps), SecArch approval, and business criticality. Default pattern = re-platform to ECS Fargate + RDS; re-architect only where messaging/ETL requires it (Service Bus, Data Factory)." | "If criteria aren't agreed up front, apps get inconsistent 7R calls → rework and SecArch churn. IMAT in particular may be mis-sized as re-platform when it's really re-architect." | Feeds Azure→AWS Mapping (per-service disposition) + per-app disposition (SMAP/IPORT/IMAT/.com). Depends on SecArch approval criteria (RACI / Governance). | "Agree the disposition decision-tree + who signs off, before per-app dispositioning begins." | "[VR architect + Parametric app owner + Morgan Stanley SecArch]"
2 | Constraints | What technical, business, regulatory or platform constraints could influence disposition? | Core
3 | Approval | Who reviews and approves the resulting application disposition? | Core
4 | Prior dispositions | What did previous Application Dispositions consist of, and in what order did they unfold? Was it kicked off formally, or did it begin with SecArch? | Core | [5 empty] | # | Strategy | What it means | Effort
5 | Prior dispositions | How much do Application Dispositions vary from one application to another, and what drives the variation? | Core | [5 empty] | 1 | Retire | Turn it off — no longer needed | None
6 | Prior dispositions | Can we walk through one or two completed Application Dispositions as examples? | Core | [5 empty] | 2 | Retain | Leave it where it is (not migrating now) | None
7 | Process | Are there steps that always must happen, such as SecArch review? | Core | [5 empty] | 3 | Rehost | "Lift & shift" — move as-is, no code change (e.g. VM → EC2) | Low
8 | Process | If the Application Disposition process is documented, where can we get that documentation and who owns it? | Core | [5 empty] | 4 | Replatform | Move with small optimizations — "lift, tinker & shift" (e.g. App Service → ECS Fargate; SQL → RDS) | Medium
9 | Teams involved | Beyond SecArch, what teams typically need to be involved? | Core | [5 empty] | 5 | Repurchase | Replace with a different product/SaaS | Varies
10 | Teams involved | At what point in the process is each team engaged, and what does each team provide or decide? | Core | [5 empty] | 6 | Re-architect / Refactor | Significantly change the code/design (e.g. Service Bus → SQS/SNS; Data Factory → Glue) | High
11 | Decision criteria | What criteria determine the target disposition (EVS, Radius, EC2, SaaS or retire)? | Core | [5 empty] | 7 | Relocate | Move at the hypervisor level (e.g. VMware → VMware Cloud on AWS) | Low–Med
12 | Decision criteria | Who makes and approves the final disposition decision? | Core
13 | Tooling and data | What information must be available before a disposition can start (current/target architecture, network flows, dependencies)? | Core
14 | Timing and outcomes | How long does a typical Application Disposition take from start to finish? | Core
15 | Timing and outcomes | How are approved dispositions revisited or changed when scope or priorities change? | Core
16 | Existing AWS work/baseline | What prior AWS or MS application pre-disposition assessments already exist, and which findings are inputs to this framework? | Core
17 | Dependencies/Disposition | How are application dependencies and shared-service dependencies incorporated into the disposition decision? | Core
18 | Platform readiness | How does readiness of the target platform or required shared services affect the disposition decision? | Core
19 | Validation | What would constitute a successful validation of the disposition framework on the representative Digital applications? | Core
20 | Cost & Licensing | What SQL Server / Windows / third-party licenses apply, and are they BYOL or Azure-included? | Other Prod-ready
21 | Cost & Licensing | Are there software products that are licensed per-core or per-socket that affect right-sizing? | Other Prod-ready
22 | Cost & Licensing | What are current Azure monthly costs for this app (compute, DB, storage, egress)? | Other Prod-ready
23 | Cost & Licensing | Any committed-use/reserved commitments on Azure that constrain decommission timing? | Other Prod-ready
24 | Cost & Licensing | Are there data-egress-heavy flows that will incur AWS transfer cost or need redesign? | Other Prod-ready
25 | Dependency Disposition | For EACH shared service used (AD, DNS, Splunk, Jenkins, SMTP, SFTP, ServiceNow, backup, scanners): does it MUST-move-before? | Other Prod-ready
26 | Dependency Disposition | For EACH shared service: can it STAY on-prem/Azure while this app moves? | Other Prod-ready
27 | Dependency Disposition | For EACH shared service: must it move WITH this app (same cutover)? | Other Prod-ready
28 | Dependency Disposition | For EACH shared service: can it move LATER than this app? | Other Prod-ready
29 | Dependency Disposition | For EACH shared service: is it ONLY a DC-exit blocker (keep until the very end)? | Other Prod-ready
30 | Dependency Disposition | Does this app share a database with another app such that they must cut over together? | Other Prod-ready
31 | Dependency Disposition | Is this app part of a batch/job chain where ordering with other apps matters at cutover? | Other Prod-ready
32 | Dependency Disposition | Does any OTHER app depend on this app being migrated first (reverse prerequisite)? | Other Prod-ready
33 | Compliance | What data retention and legal-hold obligations apply to this app's data? | Other Prod-ready
34 | Compliance | Are there data residency constraints that fix region to us-west-2 / us-east-1? | Other Prod-ready
35 | Compliance | Are there audit evidence requirements for the migration itself (who approved, when)? | Other Prod-ready
36 | Compliance | Does decommissioning the Azure resources require certified data destruction? | Other Prod-ready
37 | Documentation & Knowledge | Where is current architecture / runbook / network documentation, and is it accurate? | Other Prod-ready
38 | Documentation & Knowledge | Who holds tribal knowledge not captured in docs (key-person risk)? | Other Prod-ready
39 | Documentation & Knowledge | What CMDB/asset system tracks this app and will it be updated post-migration? | Other Prod-ready
39 questions (Application Dispositioning Framework).

## Data-DB Deep Dive
Data / DB Inventory Deep Dive
# | Topic | Question | Source | Answer (capture live) | Risk | Dependency | Decision needed | Owner
1 | Database inventory | What databases/data stores support SMAP, IPORT, IMAT and .com today? Include engine, version, hosting model and environment. | Core
2 | Inventory & app mapping | What data stores support each application, which apps use them, which are shared, and which are systems of record vs reporting/cache/analytics? | Core
3 | Workload characteristics | For each major store, is the workload OLTP, OLAP/analytics, mixed, cache/search or lake, and what are its load characteristics (read/write ratio, peak TPS, connections, size, growth)? | Core
4 | Performance | What are current DB performance characteristics and pain points (p95/p99 latency, IOPS/throughput, locking, connection pressure, slow reporting)? | Core
5 | Compatibility | What DB-specific features or cross-database dependencies could constrain migration (stored procs, jobs, linked servers, extensions, replication, triggers, shared schemas)? | Core
6 | Data engineering | What ETL/ELT, reporting, BI, batch, CDC or streaming workloads depend on these stores, and what are their schedules and freshness requirements? | Core
7 | Azure coupling | What Azure-specific dependencies exist around the data platform (Managed Identity, Key Vault, Private Endpoints, Data Factory, Synapse, Functions, Storage)? | Core
8 | Migration constraints | Given DB size, change rate, downtime tolerance and RPO, what migration approaches are feasible (backup/restore, DMS full-load + CDC, replication, export/import)? | Core
9 | Validation & rollback | How will migrated data be validated, and if users write after cutover, how will rollback/reverse sync preserve consistency? | Core
10 | HA / DR | What availability, RTO/RPO, backup/restore and DR requirements must the AWS target satisfy, and what recovery capabilities have been tested? | Core
11 | Security & connectivity | How do apps/users authenticate to the DB, what encryption requirements apply, and what private-network/firewall connectivity is required? | Core
12 | Wave sequencing | Can the application migrate while its DB stays in Azure/on-prem? Can the DB move first? Or must DB and apps move together? | Core
13 | Target / exit | What MS-approved AWS database patterns apply, and what prevents the Azure database from being decommissioned after migration? | Core
14 | Data | Which databases does this app use (Azure SQL DB, Managed Instance, Elastic Pool member)? | Other Prod-ready
15 | Data | Is the database SHARED with other applications? If so, which ones? | Other Prod-ready
16 | Data | What is the database size (GB) and daily change/transaction volume? | Other Prod-ready
17 | Data | What SQL Server version/compat level and are there cross-DB queries, linked servers, SQL Agent jobs? | Other Prod-ready
18 | Data | Are there CLR assemblies, Service Broker, FileStream, or features unsupported on RDS for SQL Server? | Other Prod-ready
19 | Data | What is the acceptable data-loss window (RPO) for this database? | Other Prod-ready
20 | Data | Can we use AWS DMS with CDC for near-zero-downtime, or is a backup/restore cutover acceptable? | Other Prod-ready
21 | Data | Are there Elastic Pool co-tenants that must be split or kept together on RDS? | Other Prod-ready
22 | Data | What are the current DB HA/DR settings (geo-replication, failover groups, backup retention)? | Other Prod-ready
23 | Data | Does the app use any NoSQL / MongoDB / Cosmos DB / Redis-persisted data? | Other Prod-ready
24 | Data | What file/blob storage does the app read/write (Azure Blob, Files)? Size and access pattern? | Other Prod-ready
25 | Data | Are there batch/ETL jobs via Data Factory that touch this app's data? | Other Prod-ready
26 | Data Migration Logistics | Total data to move for this app (DB + blob + files) in GB/TB? | Other Prod-ready
27 | Data Migration Logistics | Given Direct Connect capacity, is online transfer feasible in the window, or is offline (Snowball) needed? | Other Prod-ready
28 | Data Migration Logistics | Is there data that must be masked/anonymized for non-prod targets? | Other Prod-ready
29 | Data Migration Logistics | Are there large historical/cold datasets that can go to S3 Glacier rather than hot storage? | Other Prod-ready
30 | Data Migration Logistics | What data reconciliation / checksum method proves the migration is complete and correct? | Other Prod-ready
31 | Data Migration Logistics | Are there in-flight transactions or event backlogs that must drain before cutover? | Other Prod-ready
32 | Data & Analytics | For each data store, is the workload TRANSACTIONAL (OLTP) or ANALYTICAL (OLAP/reporting)? Or mixed (HTAP)? | Other Prod-ready
33 | Data & Analytics | Are heavy reports/analytics run against the PRODUCTION transactional DB today (contention risk)? | Other Prod-ready
34 | Data & Analytics | What is the read:write ratio and are reads scalable via replicas? | Other Prod-ready
35 | Data & Analytics | What data warehouse / BI / reporting platform exists (Synapse, Power BI, Tableau)? Fed how? | Other Prod-ready
36 | Data & Analytics | What ETL/ELT pipelines (Data Factory) move/transform data, their schedules and SLAs? | Other Prod-ready
37 | Data & Analytics | Is there streaming/real-time analytics (Event Hubs/Stream Analytics) vs batch? Latency need? | Other Prod-ready
38 | Data & Analytics | What are data volumes & growth rate per store (hot/warm/cold), and retention tiers? | Other Prod-ready
39 | Data & Analytics | Are there large joins/aggregations/scans that drive sizing (analytical heavy lifting)? | Other Prod-ready
40 | Data & Analytics | What data-freshness SLA do consumers need (real-time, hourly, daily)? | Other Prod-ready
41 | Data & Analytics | Is there CDC / change-data-capture feeding downstream systems or lakes today? | Other Prod-ready
42 | Data & Analytics | Are there data-quality, reconciliation, or master-data processes that must be preserved? | Other Prod-ready
43 | Data & Analytics | Is there a data lake / blob-based analytics today? Format (Parquet/CSV), partitioning? | Other Prod-ready
43 questions (Data / DB Inventory Deep Dive).

## Program Roadmap
Program Roadmap / Wave Plan
# | Topic | Question | Answer (capture live) | Delivery Risk | Dependency | Decision needed | Owner
1 | Dependency validation | Does our proposed dependency map and move-group structure correctly represent what must move together? What dependencies are missing? | "Team confirmed IPORT + IMAT share one SQL database → must move together. (Was a hypothesis — now validated.) No other shared-DB couplings found." | "If split across waves, shared DB breaks one app at cutover — high integrity risk." | D-01 / D002+D003: IPORT → Shared SQL; IMAT → Shared SQL (Must-move-with) | "Confirm shared-DB → lock IPORT+IMAT into MG-02 / Wave 2." | "[Parametric data/app lead]" | "These questions pressure-test the wave plan-dependencies, pilot, gates,cutover,testing"
2 | Prerequisites / hybrid | For each move group, what must be ready before it moves, what can remain hybrid temporarily, and what is only a final DC-exit dependency?
3 | Platform readiness | What are the actual readiness dates or blockers for LZ, Radius/Red Zone, networking, security, IAM, observability, CI/CD?
4 | Pilot | Which workload should prove the migration pattern first, and what must the pilot demonstrate before later waves?
5 | Sequencing | Why can't each proposed move group move one wave earlier, and which groups can run in parallel vs serial?
6 | Timing constraints | What business blackouts, release freezes, SME/resource limits, vendors, partner changes or lead times constrain the roadmap?
7 | Technical constraints | Do database/data, traffic, performance, latency, batch, scaling or rollback requirements require changing any proposed wave?
8 | Governance | What SecArch, architecture, CAB, service-onboarding, business or operational approvals are required before each wave?
9 | Wave gates | What must be true to enter a wave, what must be proven to exit it, and what stabilization/rollback period is required?
10 | Final validation | What assumptions/open decisions remain, what residual services prevent DC exit, and does Parametric/MS agree with the sequence?
11 | Operations | Who operates the app day-to-day and what runbooks exist?
12 | Operations | What is the current patching / maintenance process?
13 | Operations | Are there batch schedules / job chains (and sequence dependencies between apps)?
14 | Operations | What support tooling is used (ServiceNow, PagerDuty)? Integration points?
15 | Operations | What manual steps exist in a typical deploy or recovery?
16 | Cutover | What is the preferred cutover approach: big-bang, blue/green, or phased?
17 | Cutover | What validation/smoke tests prove the app is healthy post-cutover?
18 | Cutover | What is the rollback plan and how long does rollback take?
19 | Cutover | For the database, is bidirectional sync needed for rollback safety?
20 | Cutover | What DNS/traffic-shift mechanism is used at cutover and what is the TTL?
21 | Cutover | Who are the go/no-go approvers and what is the escalation path?
22 | Cutover | Is there a 'cutover rehearsal' / dress-rehearsal expectation before the real cutover?
23 | Cutover | What hypercare period and staffing is expected post-cutover?
24 | Cutover | Is a parallel-run (old + new live simultaneously) required for assurance?
25 | Testing & Validation | What test suites exist (unit/integration/e2e/perf) and can they run against the AWS target?
26 | Testing & Validation | What are the key user journeys that MUST be validated post-cutover?
27 | Testing & Validation | Is a performance/load baseline available to compare pre vs post migration?
28 | Testing & Validation | What security/pen-test or control validation must pass before go-live (SecArch)?
29 | Testing & Validation | How is data integrity validated after migration (row counts, checksums, business reconciliation)?
29 questions (Program Roadmap / Wave Plan).

## Integrations
Integrations — on-prem & third-party systems these portals touch (from AWS target-state diagram). Apply the 5-question disposition.
System | Type | Role / data | Used by (apps) | Disposition (retain/migrate/exit) | Must move BEFORE? | Can STAY (hybrid)? | Move WITH? | DC-exit blocker? | Owner | Notes
PCR | On-prem | Portfolio & client data | SMAP/IPORT/IMAT | Retain (hybrid via Direct Connect) | No | Yes | No | Yes
Argos | On-prem | Risk & analytics data | IMAT/IPORT | Retain (hybrid via Direct Connect) | No | Yes | No | Yes
Union | On-prem | Trade processing data | IPORT | Retain (hybrid via Direct Connect) | No | Yes | No | Yes
Okta | 3rd-party (retained) | Identity / SSO (SAML/OIDC) | All | Retain | Yes | Yes | No | No |  | Federation must exist Wave 0
SendGrid | 3rd-party (retained) | Transactional email (API) | .com/IPORT | Retain | No | Yes | No | No
DataDog | 3rd-party (retained) | Application monitoring | All | Retain | No | Yes | No | No
Glassbox | 3rd-party (retained) | Digital experience analytics | .com | Retain | No | Yes | No | No
Coveo | 3rd-party (retained) | Enterprise search | .com | Retain | No | Yes | No | Yes
Snowflake | External data (retained) | Data warehouse (JDBC/ODBC) | IMAT/analytics | Retain | No | Yes | No | No
MongoDB Atlas | External data (retained) | Document DB (VPC peering) | varies | Retain | No | Yes | No | No
Salesforce | External data (retained) | CRM integration (REST API) | varies | Retain | No | Yes | No | No
Splunk | On-prem logging | Centralized logging | All | Migrate at DC-exit | No | Yes | No | Yes |  | SPLUNK RULE: Wave-0 connectivity; migrate at exit
Active Directory | On-prem identity | Auth / directory | All | Migrate at DC-exit | No | Yes | No | Yes |  | Federate via Okta during hybrid
MS ETS (Enhanced Technology Support) | MS-provided managed service | Managed support / possible VMware SDDC hosting (AWS-architect hint) | Context only | Out of scope — context only (MS-operated) | No | Yes | No | No |  | HINT to confirm (see LZ Prod-Ready Qs): not a migration target; verify it's not in the 4 apps' data path

## Azure → AWS Mapping
Azure → AWS Landing Zone Mapping — POST-WORKSHOP design worksheet
Use as : capture the Azure as-is estate LIVE on the 'Platform · LZ-Radius' and 'Data-DB Deep Dive' tabs during the workshop (discovery is fast). Then COME BACK HERE and fill/confirm the AWS landing-zone target design. Rows are seeded DRAFT — edit and confirm, don't start blank. Scope = the 4 apps (Azure→AWS); on-prem systems and MS ETS/VMware are context, not targets.
Layer | Azure (as-is) — confirm in discovery | AWS landing-zone target (to-be) | Disposition / pattern | Discovered yet? | Owner | Notes
Networking | VNet(s) + hub/spoke or peering topology | VPC + Transit Gateway (hub/spoke) | Re-architect to AWS LZ |  |  | Confirm app placement + address plan
Networking | Public / private subnets | Public + private subnets across AZs | Re-platform |  |  | Multi-AZ per availability requirement
Network security | Azure Firewall / NSGs / egress controls | Network Firewall + Security Groups / NACLs + egress | Re-architect |  |  | Map app-to-dependency flows -> SG rules
Connectivity (hybrid) | VNet-to-on-prem / ExpressRoute | Direct Connect / VPN to on-prem (PCR/Argos/Union stay) | Retain (hybrid) |  |  | On-prem stays — connectivity only
DNS | Azure DNS private zones | Route 53 private hosted zones | Re-platform |  |  | Which names must resolve across hybrid boundary
DNS | Azure public DNS | Route 53 public hosted zones | Re-platform |  |  | Edge path: Akamai -> WAF -> R53 -> ALB
Identity / security | Entra ID / Managed Identity | IAM roles + Okta federation | Re-architect |  |  | Okta federation ready Wave 0
Identity / security | Azure Key Vault (33 vaults) | AWS Secrets Manager + KMS | Re-platform |  |  | Secrets + encryption keys
Compute | Azure App Service — 397 web apps (containerize) | Amazon ECS Fargate | Re-platform (IMAT: refactor flagged) |  |  | Per-app; see app tabs
Data | Azure SQL Database — 77 DBs | Amazon RDS for SQL Server (Multi-AZ), via DMS | Re-platform |  |  | IPORT+IMAT share one DB -> move together
Data | Azure Blob Storage — 30 accounts (~24 TB) | Amazon S3 | Re-platform |  |  | Static/content + objects
Messaging | Azure Service Bus — 10 Premium namespaces | Amazon SQS / SNS / EventBridge | Re-architect (VR: code change) — AWS doc labels Re-platform |  |  | Confirm which apps use messaging
Observability | Azure Monitor / App Insights / Log Analytics — 44 resources | Amazon CloudWatch + X-Ray + DataDog | Re-platform |  |  | DataDog stays per Integrations
Logging | Log sinks | CloudWatch Logs + Splunk connectivity (hybrid) | Re-platform |  |  | SPLUNK RULE: Wave-0 connectivity; Splunk migrates at DC-exit
API management | Azure API Management — 17 instances | Amazon API Gateway | Re-platform |  |  | Front-door for app APIs (17 insatnces will many APIs)
Caching | Azure Cache for Redis — 10 | Amazon ElastiCache | Re-platform |  |  | Session/cache tier
Messaging | Azure Event Hubs — 4 namespaces | Amazon Kinesis | Re-architect (VR: code change) — AWS doc labels Re-platform |  |  | Streaming ingest — confirm which apps
Data integration / ETL | Azure Data Factory v2 — 12 factories | AWS Glue + Step Functions | Re-architect |  |  | Only Re-architect in AWS target-state — pipelines rebuilt
Seeded rows are the standard target design — confirm or correct each after discovery. Add rows for any Azure resource found that isn't listed.

## Dependency Register
Dependency Register — one row per dependency edge. Populated live from the app tabs + Integrations. Feeds the Engine -> Move Groups -> Waves.
Dep ID | From (app/svc) | To (dependency) | Type | Must move BEFORE? | Can STAY? | Move WITH? | Move LATER? | DC-exit blocker? | Disposition (derived) | Notes
D001 | SMAP | AWS LZ / landing zone | Network | Yes | No | No | No | No | Must-move-before | Wave-0 prerequisite
D002 | IPORT | Shared SQL | Database | Yes | No | Yes | No | No | Must-move-with | IPORT+IMAT share one DB
D003 | IMAT | Shared SQL | Database | Yes | No | Yes | No | No | Must-move-with | IPORT+IMAT share one DB
D004 | ALL | Splunk (on-prem) | Logging | No | Yes | No | Yes | Yes | Can-remain-temporarily | Wave-0 connectivity; migrate at DC-exit
D005 | ALL | Okta | Identity | Yes | Yes | No | No | No | Must-move-before | Federation ready Wave 0
Rows D001–D005 are worked examples — add real dependencies captured in the workshops below.
D001 = SMAP → AWS Landing Zone (must move before) D002 = IPORT → Shared SQL (must move with) D003 = IMAT → Shared SQL (must move with) D004 = ALL → Splunk (can stay temporarily) D005 = ALL → Okta (must move before)

## RAID Log
RAID Log — Risks · Assumptions · Issues/Decisions · Dependencies (rollup register)
How to use: ROLLUP only — do NOT capture here first. Teams capture live on the app/shared tabs (Risk / Dependency / Assumption / Decision columns); consolidate the OPEN items into this one log for weekly status, the steering deck, and the Program Roadmap. One source of truth. Status: Open = raised, not yet resolved · Deferred = consciously parked pending a workshop/MS input (always set a Due/target so it isn't lost) · Closed = decided (note the resolution).
ID | Type | Item | Related app / workshop | Owner | Status | Due / target | Notes / resolution | D-01, D-02 = Decisions R-01, R-02 = Risks A-01, A-02 = Assumptions (and I- would be Issues)
D-01 | Decision | Confirm IPORT + IMAT share one SQL DB → must move together (Wave 2) | App · IPORT / IMAT; Data-DB Deep Dive |  | Deferred | Portfolio Review | Drives move-group MG-02; validate in workshop
D-02 | Decision | Confirm MS ETS / VMware SDDC is NOT in the data path of the 4 apps → out of scope | Platform · LZ-Radius |  | Deferred | LZ workshop | AWS-architect hint; see LZ Prod-Ready Q + Integrations context row
D-03 | Dependency | Okta identity federation(3rd-party identity/SSO system) ready before Wave 0 | Platform · LZ-Radius; RACI |  | Open | Wave 0 | Enabler for all app moves
D-04 | Dependency | AWS→Splunk connectivity at Wave 0; Splunk migrates at DC-exit | Integrations; Program Roadmap |  | Open | Wave 0 / DC-exit | SPLUNK RULE — connectivity now, platform migrates at exit
R-01 | Risk | .com has the most public exposure → sequenced last (Wave 4) | App · .com; Wave Plan |  | Open | Wave 4 | Apply proven pattern last to limit blast radius
R-02 | Risk | IMAT flagged as refactor candidate — effort/scope not yet sized | App · IMAT; App Dispositioning |  | Open | Portfolio Review | Confirm refactor vs replatform in disposition
A-01 | Assumption | On-prem (PCR / Argos / Union) stays put — hybrid connectivity, not migrated | Integrations |  | Open | — | Out of migration scope; validate connectivity needs
A-02 | Assumption | Azure SQL → Amazon RDS for SQL Server (Multi-AZ) is the target data pattern | Azure → AWS Mapping; Data-DB Deep Dive |  | Open | Data deep-dive | Confirm per app after discovery
D-05 | Decision | MG-03 messaging in scope — AWS target-state confirms Azure Service Bus (10 Premium ns) -> SQS/SNS/EventBridge and Event Hubs (4 ns) -> Kinesis. Confirm: (a) which of the 4 apps publish/consume messaging, (b) whether MG-03 stands alone at Wave 3 or messaging moves WITH its consuming apps, (c) batch-chain dependencies. | Wave Plan (MG-03); Azure -> AWS Mapping; App tabs has questions for this |  | Open | Brainstorm | Confirmed by AWS->Parametric proposal (target-state diagram). Keep MG-03 at Wave 3 as draft; this item resolves standalone-vs-rides-with-apps.
Seeded rows are known open items — update Owner/Status/Due as workshops resolve them, and add new items consolidated from the app/shared tabs. Note the are seeded drafts/hypotheses

## Wave Plan
Wave Plan — Move Groups scored into Waves (computed from dependencies + readiness + risk; criticality is a modifier). DRAFT — validate in Program Roadmap workshop.
Move Group | Members | Prereq (must-move-before) | Shared coupling | Complexity | Business crit. | -> Wave | Rationale
MG-00 | AWS LZ, TGW/DX, IAM/Okta, Red Zone, observability | — (foundation) | n/a | Med | Enabler | Wave 0 | Foundation every app depends on. | MG-00 = the foundation (LZ, networking, IAM) → Wave 0 MG-01 = SMAP → Wave 1 MG-02 = IPORT + IMAT (share a DB) → Wave 2 MG-03 = messaging/batch apps → Wave 3 MG-04 = .com → Wave 4 MG-DX = DC-exit residuals (Splunk/AD)
MG-01 | SMAP | MG-00 | Standalone | Low | Medium | Wave 1 | Lowest-coupled — proves ECS Fargate + RDS + edge pattern.
MG-02 | IPORT + IMAT + shared SQL | MG-00, MG-01 | Shared SQL | Med | Medium | Wave 2 | Share one database -> must move together.
MG-03 | Messaging / batch-chain apps | MG-00, MG-02 | Service Bus / Event Hubs | High | Medium | Wave 3 | Cross-system + hybrid complexity.
MG-04 | .com | MG-00..03 | Mostly independent; Red Zone | High | Critical | Wave 4 | Most public exposure; applies proven pattern last.
MG-DX | Splunk / AD / SFTP residuals | all app waves done | DC-exit blockers | Med | Varies | DC Exit | Residual shared services migrate at final DC-exit.